## README
Limerick residential delivery study – data companion
Scheme | A counted residential application from the Limerick pipeline workbook (after primacy rules), plus residential Part 8 schemes in the planning register that CIS does not hold (Source column).
Owner / sector | Public = Limerick City and County Council (incl. Part 8), approved housing bodies, Land Development Agency. From CIS grantee and promoter, building control local-authority and AHB flags, and Part 8 file numbers (yy/8nnn). Turnkey purchases not identified in these sources are classed as private.
City neighbourhood | Nine neighbourhoods defined by Limerick City and County Council from 42 Electoral Divisions (King’s Island, code 1a, shown separately). Schemes outside them are labelled Outside city neighbourhoods.
Planning dates | National Planning Applications dataset (Department of Housing, Local Government and Heritage), Limerick County Council records, queried 29/09/2026. An Coimisiún Pleanála case pages for SHD. CIS dates for Part 8 schemes.
Start on site | Earliest commencement date on a building control commencement notice (National Building Control Office open data, 2014–present) matched by planning reference, including extensions of duration and appeal references. CIS start date used only where no notice matched and CIS records the scheme on site or complete.
Completion | CIS. Date of the first dated CIS update recording the scheme as complete; CIS finish date where no such update exists. Completion certificates were tested but record 328 of the 1,226 units CIS reports complete on the same schemes, so they are not used for completions.
Status | Complete (CIS); Under construction (commencement notice or CIS on site / part complete); Not started – permission live; Not started – past expiry (register expiry, including extensions of duration, before 29/09/2026). Part 8 schemes have no register expiry.
Size bands | 1–9, 10–24, 25–49, 50–99, 100+ units (CIS units).
LEA | Point-in-polygon against Local Electoral Areas 2019 (Tailte Éireann, generalised 20m).
Durations | Approval = application received to final grant (appeal decision date where appealed). Grant to start = final grant to first commencement. Build period = start to completion. Negative intervals (data errors) are dropped.
Formulas | Status, expiry and LEA count/sum tables are live formulas on the Schemes sheet. Medians, quartiles and cumulative start shares were calculated in Python (delivery_analysis.py) and are values.
Contacts | No personal data. Scheme names are CIS project headings.

## Schemes
Planning ref | Register ref | Source | Site ID | Scheme | Settlement | LEA | City neighbourhood | Latitude | Longitude | Units | Size band | Type | Route | Owner | Sector | CIS stage | Status | Application received | Permission granted | Further information | Appealed | Expiry | Start on site | Start source | Commencement notices | Units on notices | Completion (CIS) | Completion certificates | Units on certificates | Approval (yrs) | Grant to start (yrs) | Build period (yrs) | Build rate (dpa) | Relationship | Relationship confidence | CIS notes on barriers | Completion source | Social housing project no. | Social housing programme | Social housing stage | Social housing stage quarter | Public delivery mode
22990 | 22990 | CIS | SG-015 | €22m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5587 | -8.7982 | 99 | 50–99 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-09-13 | 2025-02-25 | Yes | Yes | 2030-02-24 |  |  | 0 | 0 |  | 0 | 0 | 2.4531 |  |  |  | Additional application on site | Low
21630 | 21630 | CIS | U-1166991 | €10.8m - Residential Development, Croom | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.525 | -8.7171 | 51 | 50–99 | Houses | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2021-05-12 | 2022-05-12 | Yes | No | 2027-05-11 |  |  | 1 | 12 |  | 0 | 0 | 0.99932 |  |  |  | Primary | High
22410 | 22410 | CIS | P-1225380 | €18.8m - Nursing Home Development, Croom | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.5222 | -8.7125 | 32 | 25–49 | Unknown | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-04-11 | 2023-02-20 | Yes | No | 2028-02-19 |  |  | 0 | 0 |  | 0 | 0 | 0.86242 |  |  |  | Primary | High
198010 | 198010 | CIS | SG-015 | €5m - Housing Development | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5575 | -8.7986 | 31 | 25–49 | Apartments | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2019-10-21 | 2020-01-27 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.26831 |  |  |  | Primary | High
24352 | 24352 | CIS | P-1366163 | €7.3m - Residential Development | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.6491 | -8.8668 | 30 | 25–49 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2024-09-12 | 2025-09-17 | Yes | No | 2030-09-16 | 2025-12-22 | Commencement notice | 1 | 30 |  | 0 | 0 | 1.013 | 0.26283 |  |  | Primary | High
2660779 | 2660779 | CIS | P-1444384 | €8.6m - Staff Accommodation/8Apartments, Adare | Adare | Adare-Rathkeale | Outside city neighbourhoods | 52.5617 | -8.7658 | 28 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2026-07-09 | 2026-09-02 | No | No | 2031-09-02 |  |  | 0 | 0 |  | 0 | 0 | 0.15058 |  |  |  | Primary | High
2360793 | 2360793 | CIS | SG-015 | €6.1m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5584 | -8.7997 | 28 | 25–49 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2023-11-01 | 2025-03-21 | No | Yes | 2030-03-20 |  |  | 0 | 0 |  | 0 | 0 | 1.3854 |  |  |  | Additional phase | Medium
2460304 | 2460304 | CIS | SG-015 | €6.2m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5606 | -8.7984 | 25 | 25–49 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-04-09 | 2025-03-21 | No | Yes | 2030-03-20 |  |  | 0 | 0 |  | 0 | 0 | 0.9473 |  |  |  | Additional phase | Medium
198005 | 198005 | CIS | P-1058813 | €1.7m - Residential Development | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.5231 | -8.7172 | 16 | 10–24 | Mixed | Part 8 / council | Public – approved housing body | Public | Complete | Complete | 2019-07-22 | 2021-10-29 | No | No |  | 2024-01-22 | Commencement notice | 1 | 16 | 2025-12-22 | 1 | 1 | 2.2724 | 2.2313 | 1.9165 | 8.3486 | Primary | High |  | CIS | 1927 | CAS AHB Construction | Completed | Q4-2025 | Construction
19552 | 19552 | CIS | P-1051821 | €2m - Apartment Development | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.5247 | -8.7145 | 14 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2019-06-07 | 2020-11-13 | Yes | Yes | 2028-11-13 |  |  | 0 | 0 |  | 0 | 0 | 1.4374 |  |  |  | Primary | High
20525 | 20525 | Register only (private, not in CIS) |  | Register: the construction of 14 dwelling houses, including 2 no semi-detached 2 | Croom | Adare-Rathkeale | Outside city neighbourhoods | 52.5231 | -8.7188 | 14 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2020-06-19 | 2021-12-02 | Yes | Yes | 2026-12-01 |  |  | 0 | 0 |  | 0 | 0 | 1.4538 |  |  |  | Primary
Part 8 - 1345677 | Part 8 - 1345677 | CIS | P-1345677 | €1.5m - New Traveller Welfare Units, Hillview Park | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5264 | -8.9375 | 11 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2024-08-23 |  | No | No |  | 2024-11-18 | CIS start date | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2560977 | 2560977 | CIS | P-1424781 | €2.7m - Self Catering Accommodation Lodges, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | 52.5546 | -8.7894 | 10 | 10–24 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2025-09-26 | 2026-03-23 | Yes | No | 2031-03-22 | 2026-06-01 | Commencement notice | 1 | 0 |  | 0 | 0 | 0.48734 | 0.19165 |  |  | Primary | High
24151 | 24151 | Register only (private, not in CIS) |  | Register: the construction of 10 dwelling units to include 2 no. detached 5 bedr | Croom | Adare-Rathkeale | Outside city neighbourhoods | 52.516 | -8.7205 | 10 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-04-12 | 2025-01-15 | Yes | No | 2030-01-14 |  |  | 0 | 0 |  | 0 | 0 | 0.76112 |  |  |  | Primary
20314 | 20314 | CIS | P-1098119 | €1.1m - 6 Houses | Adare | Adare-Rathkeale | Outside city neighbourhoods | 52.5845 | -8.7688 | 6 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2020-04-14 | 2020-08-11 | No | No | 2025-08-10 | 2021-12-09 | Commencement notice | 1 | 6 |  | 0 | 0 | 0.3258 | 1.3279 |  |  | Primary | High
201101 | 201101 | CIS | P-1130829 | €1m - 5 Houses | Adare | Adare-Rathkeale | Outside city neighbourhoods | 52.5555 | -8.7932 | 5 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2020-10-29 | 2021-05-17 | No | Yes | 2024-05-16 | 2024-09-19 | CIS start date | 0 | 0 |  | 0 | 0 | 0.54757 | 3.3429 |  |  | Primary | High
197016 | 197016 | CIS | P-1053166 | €800k - Residential Development, Ballingarry | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.4761 | -8.8677 | 4 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2019-06-13 | 2019-09-03 | Yes | No | 2024-07-28 | 2021-08-19 | Commencement notice | 3 | 3 |  | 0 | 0 | 0.2245 | 1.9603 |  |  | Extension of duration (parent not in CIS) | Low
2360207 | 2360207 | CIS | P-1283723 | €680k - 3 Houses | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.5953 | -9.1866 | 3 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2023-04-10 | 2023-09-18 | Yes | No | 2026-09-17 |  |  | 0 | 0 |  | 0 | 0 | 0.44079 |  |  |  | Primary | High
2460299 | 2460299 | CIS | P-1339954 | €884k - 3 Houses | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | 52.4596 | -8.7608 | 3 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-04-05 | 2024-07-02 | No | No | 2029-07-01 |  |  | 0 | 0 |  | 0 | 0 | 0.24093 |  |  |  | Primary | High
2360794 | 2360794 | CIS | P-1316492 | €15.3m - Residential Development, Bruff | Bruff | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4724 | -8.5493 | 74 | 50–99 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2023-11-01 | 2024-05-07 | Yes | No | 2029-05-06 |  |  | 0 | 0 |  | 0 | 0 | 0.51472 |  |  |  | Primary | High | Site for sale / sold
2460788 | 2460788 | CIS | P-1360674 | €7.4m - Residential Development, Kilmallock | Kilmallock | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3973 | -8.5779 | 42 | 25–49 | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2024-08-06 | 2025-07-15 | Yes | No | 2030-07-14 | 2026-04-06 | Commencement notice | 1 | 28 |  | 0 | 0 | 0.93908 | 0.72553 |  |  | Primary | High
191298 | 191298 | CIS | P-1084266 | €5.6m - Housing Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6506 | -8.3968 | 32 | 25–49 | Houses | Standard planning application | Private | Private | Stalled or Suspended | Not started – permission live | 2019-12-23 | 2020-11-26 | Yes | No | 2028-11-25 |  |  | 0 | 0 |  | 0 | 0 | 0.92813 |  |  |  | Primary | High | On hold / no movement
2326 | 2326 | CIS | P-1266613 | €6.3m - Housing Development, Kilmallock | Kilmallock | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4027 | -8.5838 | 28 | 25–49 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2023-01-18 | 2024-01-29 | Yes | No | 2029-01-28 | 2026-03-28 | Commencement notice | 1 | 28 |  | 0 | 0 | 1.0294 | 2.1602 |  |  | Primary | High
2461182 | 2461182 | CIS | P-1379266 | €5.4m - Residential Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6051 | -8.2512 | 27 | 25–49 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-11-29 | 2026-03-30 | Yes | Yes | 2031-03-29 |  |  | 0 | 0 |  | 0 | 0 | 1.3306 |  |  |  | Primary | High
23529 | 23529 | CIS | P-1317302 | €4.4m - Housing Development | Cappamore | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6124 | -8.3358 | 22 | 10–24 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2023-11-07 | 2024-09-03 | Yes | No | 2029-09-02 | 2025-10-09 | Commencement notice | 1 | 22 |  | 0 | 0 | 0.82409 | 1.0979 |  |  | Primary | High
19149 | 19149 | CIS | U-1034286 | €567k - Change of Use to Care Residential Units | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6039 | -8.2448 | 21 | 10–24 | Apartments | Standard planning application | Public – approved housing body | Public | Tender | Not started – past expiry | 2019-02-20 | 2019-09-11 | Yes | No | 2024-09-10 |  |  | 0 | 0 |  | 0 | 0 | 0.55578 |  |  |  | Primary | High |  |  | 1937 | CAS AHB Construction | Stage 3 Pre-Tender Design | Q2-2024 | Construction
188002 | 188002 | CIS | P-981494 | €1.9m - Residential Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4725 | -8.4303 | 20 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-03-15 | 2018-05-14 | No | No |  | 2020-03-18 | Commencement notice | 1 | 20 | 2023-12-14 | 1 | 1 | 0.16427 | 1.8453 | 3.7399 | 5.3477 | Primary | High |  | CIS | 1819 | SHIP LA Construction | Completed | Q4-2023 | Construction
Part 8 - 1392454 | Part 8 - 1392454 | CIS | P-1392454 | €5.9m - Residential Development, Bruff | Bruff | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4755 | -8.5474 | 18 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2024-07-04 | 2024-10-04 | No | No |  | 2026-05-08 | CIS start date | 0 | 0 |  | 0 | 0 | 0.25188 | 1.5907 |  |  | Primary | High |  |  | 1831 | SHIP LA Construction | Stage 4 Tender Report / Final Turnkey or CALF Approval | Q4-2025 | Construction
221352 | 221352 | CIS | SG-030 | €5.5m - Housing Development, Cappamore | Cappamore | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6157 | -8.3432 | 17 | 10–24 | Houses | Standard planning application | Public – approved housing body | Public | Complete | Complete | 2022-12-15 | 2023-07-11 | Yes | No | 2028-07-10 | 2025-03-18 | Commencement notice | 1 | 17 | 2026-08-10 | 1 | 1 | 0.56947 | 1.6865 | 1.3963 | 12.175 | Primary | High |  | CIS | 1714 | CALF Construction | On Site | Q1-2025 | Construction
211170 | 211170 | CIS | P-1184979 | €3m - Modifications to Housing Development, Kilfinane | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3581 | -8.4628 | 14 | 10–24 | Houses | Standard planning application | Public – local authority | Public | On Site | Under construction | 2021-08-17 | 2022-09-16 | Yes | No | 2027-09-15 | 2024-04-22 | Commencement notice | 1 | 1 |  | 0 | 0 | 1.0815 | 1.5989 |  |  | Primary | High |  |  | 1812 | SHIP LA Turnkey | Stage 4 Tender Report / Final Turnkey or CALF Approval | Q1-2026 | Turnkey
198007 | 198007 | CIS | P-1065269 | €1.4m - Housing Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4369 | -8.408 | 12 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2019-09-02 | 2019-11-15 | No | No |  | 2021-08-13 | Commencement notice | 1 | 12 | 2024-02-15 | 1 | 1 | 0.2026 | 1.744 | 2.5079 | 4.7849 | Primary | High |  | CIS | 1821 | SHIP LA Construction | Completed | Q4-2022 | Construction
19872 | 19872 | CIS | P-1065293 | €1.3m - Care Residential Units | Cappamore | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6129 | -8.3334 | 10 | 10–24 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2019-09-02 | 2020-02-25 | Yes | No | 2025-02-24 | 2024-05-08 | Commencement notice | 1 | 10 |  | 0 | 0 | 0.48186 | 4.1999 |  |  | Primary | High
218013 | 218013 | CIS | P-1205019 | €3m - Housing Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3591 | -8.4737 | 10 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2021-12-10 | 2022-03-09 | No | No |  | 2024-03-19 | Commencement notice | 1 | 10 | 2026-05-13 | 1 | 2 | 0.24367 | 2.0287 | 2.1492 | 4.6529 | Primary | High |  | CIS | 1829 | SHIP LA Construction | Completed | Q4-2025 | Construction
2148 | 2148 | CIS | P-1144674 | €1.9m - Change of Use to 9 Apartments, St. Paul's Convent | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3606 | -8.47 | 9 | 1–9 | Apartments | Standard planning application | Public – approved housing body | Public | Complete | Complete | 2021-01-19 | 2021-10-06 | Yes | No | 2026-10-05 | 2023-11-20 | Commencement notice | 1 | 9 | 2025-10-20 | 1 | 1 | 0.71184 | 2.1218 | 1.9165 | 4.6961 | Primary | High |  | CIS | 1931 | CAS AHB Construction | Completed | Q4-2024 | Construction
21550 | 21550 | CIS | P-1164066 | €1.9m - 9 Houses | Caherconlish | Cappamore-Kilmallock | Outside city neighbourhoods | 52.5954 | -8.4712 | 9 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2021-04-28 | 2022-02-23 | Yes | No | 2027-02-22 | 2024-04-11 | Commencement notice | 1 | 7 | 2026-06-22 | 1 | 3 | 0.82409 | 2.13 | 2.1958 | 4.0988 | Primary | High |  | CIS
228000 | 228000 | CIS | P-1213266 | €2.5m - 9 Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3688 | -8.3446 | 9 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2022-02-04 | 2022-04-07 | No | No |  | 2025-04-22 | Commencement notice | 1 | 9 |  | 0 | 0 | 0.16975 | 3.0418 |  |  | Additional application on site | Low |  |  | 1828 | SHIP LA Construction | Stage 4 Tender Report / Final Turnkey or CALF Approval | Q1-2025 | Construction
2560947 | 2560947 | CIS | P-1414007 | €1m - 8 Houses, Bruff | Bruff | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4769 | -8.537 | 8 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-09-19 | 2026-09-02 | Yes | No | 2031-09-02 |  |  | 0 | 0 |  | 0 | 0 | 0.95277 |  |  |  | Primary | High
2360393 | 2360393 | CIS | SG-016 | €604k - 8 Residential Units | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4373 | -8.4086 | 8 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2023-06-08 | 2023-12-05 | Yes | No | 2028-12-04 | 2024-09-30 | Commencement notice | 1 | 4 | 2026-08-17 | 1 | 4 | 0.49281 | 0.82136 | 1.8782 | 4.2595 | Additional application on site | Low |  | CIS
2461101 | 2461101 | CIS | SG-030 | €1.4m - 7 Houses | Cappamore | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6152 | -8.3441 | 7 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-11-07 | 2025-07-30 | Yes | No | 2028-10-16 |  |  | 0 | 0 |  | 0 | 0 | 0.72553 |  |  |  | Replaces earlier | Medium
2360798 | 2360798 | CIS | SG-033 | €1.2m - 6 Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4348 | -8.4095 | 6 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2023-11-02 | 2024-10-31 | Yes | No | 2029-10-30 | 2025-07-07 | Commencement notice | 2 | 6 |  | 0 | 0 | 0.99658 | 0.68172 |  |  | Additional phase | Medium
19233 | 19233 | CIS | P-1036712 | €931k - 5 Houses | Kilmallock | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4017 | -8.5787 | 5 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2019-03-12 | 2020-03-02 | Yes | Yes | 2025-03-01 | 2024-04-19 | Commencement notice | 1 | 5 | 2025-12-09 | 1 | 3 | 0.97467 | 4.1314 | 1.64 | 3.0488 | Primary | High |  | CIS
21240 | 21240 | CIS | P-1152091 | €561k - Main Street Housing Development, Ballylanders | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.3718 | -8.3478 | 5 | 1–9 | Houses | Standard planning application | Public – local authority | Public | Complete | Complete | 2021-03-01 | 2022-05-17 | Yes | Yes | 2027-05-16 | 2023-07-21 | Commencement notice | 1 | 5 | 2024-11-15 | 1 | 2 | 1.2101 | 1.1773 | 1.3224 | 3.7811 | Primary | High |  | Department social housing report | 1804 | SHIP LA Turnkey | Completed | Q4-2024 | Turnkey
191184 | 191184 | CIS | SG-016 | €790k - 5 Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.437 | -8.4095 | 5 | 1–9 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2019-11-29 | 2020-07-28 | Yes | No | 2025-07-27 | 2021-05-05 | Commencement notice | 3 | 5 |  | 3 | 3 | 0.66256 | 0.76934 |  |  | Additional application on site | Low
2560211 | 2560211 | CIS | P-1395070 | €800k - 4 Apartments | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.6525 | -8.3987 | 4 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2025-03-15 | 2025-06-10 | No | No | 2030-06-09 | 2026-03-21 | Commencement notice | 1 | 4 |  | 0 | 0 | 0.23819 | 0.77755 |  |  | Primary | High
2360546 | 2360546 | CIS | SG-033 | €686k - 4 Dwellings | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.435 | -8.4096 | 4 | 1–9 | Apartments | Standard planning application | Private | Private | Complete | Complete | 2023-07-31 | 2023-10-24 | No | No | 2028-10-23 | 2024-01-24 | Commencement notice | 2 | 4 | 2025-10-30 | 2 | 4 | 0.23272 | 0.25188 | 1.7659 | 2.2651 | Primary | High |  | CIS
Part 8 - 1378805 | Part 8 - 1378805 | CIS | U-1378805 | €800k - Housing Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4002 | -8.2967 | 4 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2024-11-22 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2360148 | 2360148 | CIS | P-1278179 | €1.5m - 3 Community Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.5641 | -8.3379 | 3 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2023-03-15 | 2023-11-02 | Yes | No | 2028-11-01 | 2024-08-26 | Commencement notice | 1 | 0 | 2025-11-20 | 1 | 3 | 0.63518 | 0.81588 | 1.2348 | 2.4296 | Additional application on site | Low |  | CIS
15577 | 15577 | CIS | U-837963 | €588k - 3 Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.5642 | -8.3382 | 3 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Tender | Not started – permission live | 2015-07-23 | 2015-09-09 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.13142 |  |  |  | Primary | High
191255 | 191255 | CIS | P-1081912 | €572k - Residential Development, Kilmallock | Kilmallock | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4788 | -8.5476 | 2 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2019-12-17 | 2020-03-18 | No | No | 2025-03-17 | 2022-04-27 | Commencement notice | 1 | 2 | 2024-12-20 | 1 | 1 | 0.25188 | 2.1081 | 2.6502 | 0.75465 | Primary | High |  | CIS
20341 | 20341 | CIS | P-1099323 | €574k - Extension to Pub | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | 52.4122 | -8.3793 | 1 | 1–9 | Unknown | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-04-27 | 2020-09-24 | Yes | No | 2025-09-23 |  |  | 0 | 0 |  | 0 | 0 | 0.41068 |  |  |  | Primary | High
2660241 | 2660241 | CIS | P-1446288 | €125.6m - Large Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6641 | -8.5618 | 523 | 100+ | Apartments | LRD | Private | Private | Permission Granted | Not started – permission live | 2026-03-04 | 2026-04-28 | No | No | 2031-09-01 |  |  | 0 | 0 |  | 0 | 0 | 0.15058 |  |  |  | Primary | High
2660089 | 2660089 | CIS | P-1423228 | €42m - Large Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6569 | -8.5737 | 465 | 100+ | Student | LRD | Private | Private | Permission Granted | Not started – permission live | 2026-01-30 | 2026-07-22 | No | Yes | 2031-07-21 |  |  | 0 | 0 |  | 0 | 0 | 0.47365 |  |  |  | Primary | High
2660603 | 2660603 | CIS | P-1437215 | €84m - Parkway Valley LRD, Singland | Other County Limerick | Limerick City East | Southhill | 52.6602 | -8.5885 | 403 | 100+ | Apartments | LRD | Private | Private | Permission Granted | Not started – permission live | 2026-05-28 | 2026-07-22 | No | No | 2031-07-22 |  |  | 0 | 0 |  | 0 | 0 | 0.15058 |  |  |  | Primary | High
2660275 | 2660275 | CIS | P-1428325 | €42m - Large Residential Development,Limerick | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6556 | -8.5816 | 212 | 100+ | Mixed | LRD | Private | Private | Permission Granted | Not started – permission live | 2026-03-11 | 2026-09-23 | Yes | No | 2031-09-22 |  |  | 0 | 0 |  | 0 | 0 | 0.53662 |  |  |  | Primary | High
ABPREF307631 | ABPREF307631 | CIS | SG-019 | €44m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6668 | -8.5494 | 200 | 100+ | Mixed | SHD (An Bord Pleanála) | Private | Private | Complete | Complete | 2020-07-17 | 2020-11-02 | No | No | 2025-11-01 | 2022-08-30 | Commencement notice | 10 | 143 | 2024-09-20 | 15 | 23 | 0.29569 | 1.8234 | 2.0589 | 97.141 | Primary | High |  | CIS
2560113 | 2560113 | CIS | P-1389800 | €87m - Student Accommodation, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6638 | -8.5802 | 196 | 100+ | Student | LRD | Private | Private | Commencement Expected | Not started – permission live | 2025-02-12 | 2025-10-29 | Yes | No | 2030-10-28 |  |  | 0 | 0 |  | 0 | 0 | 0.7091 |  |  |  | Primary | High
ABPREF309999 | ABPREF309999 | CIS | P-1163033 | €30m - Residential Development, Annacotty | Annacotty | Limerick City East | Castletroy/Annacotty | 52.6674 | -8.5353 | 137 | 100+ | Mixed | SHD (An Bord Pleanála) | Private | Private | Permission Granted | Not started – past expiry | 2021-04-21 | 2021-08-05 | No | No | 2026-08-04 |  |  | 0 | 0 |  | 0 | 0 | 0.29021 |  |  |  | Primary | High | On hold / no movement
18434 | 18434 | CIS | SG-005 | €10m - Residential Development, Singland | Other County Limerick | Limerick City East | Southhill | 52.6575 | -8.5869 | 133 | 100+ | Mixed | Standard planning application | Private | Private | Complete | Complete | 2018-05-04 | 2018-11-06 | Yes | No | 2023-11-05 | 2020-06-22 | Commencement notice | 8 | 104 | 2025-06-26 | 11 | 29 | 0.50924 | 1.6263 | 5.0103 | 26.5455 | Primary | High |  | CIS
2360842 | 2360842 | CIS | U-1319159 | €22m - Golf Links Road LRD, Monaleen | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6527 | -8.5604 | 122 | 100+ | Mixed | LRD | Private | Private | On Site | Under construction | 2023-11-17 | 2024-05-23 | No | Yes | 2029-05-22 | 2024-12-20 | Commencement notice | 7 | 113 |  | 0 | 0 | 0.51472 | 0.57769 |  |  | Primary | High
2560271 | 2560271 | CIS | SG-002 | €21m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6631 | -8.5649 | 114 | 100+ | Mixed | LRD | Private | Private | Permission Granted | Not started – permission live | 2025-04-02 | 2026-04-15 | Yes | Yes | 2031-04-14 |  |  | 0 | 0 |  | 0 | 0 | 1.0349 |  |  |  | Additional application on site | Low
211152 | 211152 | CIS | SG-008 | €16.6m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6622 | -8.5449 | 105 | 100+ | Mixed | Standard planning application | Private | Private | Complete | Complete | 2021-08-12 | 2022-04-20 | Yes | No | 2027-04-19 | 2024-04-11 | Commencement notice | 5 | 105 | 2026-05-14 | 17 | 17 | 0.6872 | 1.9767 | 2.089 | 50.2638 | Additional application on site | Low |  | CIS
181104 | 181104 | CIS | SG-008 | €11.8m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6615 | -8.5462 | 99 | 50–99 | Apartments | Standard planning application | Private | Private | Part Complete | Under construction | 2018-11-14 | 2019-06-04 | Yes | No | 2027-06-02 | 2023-07-07 | Commencement notice | 2 | 63 |  | 7 | 29 | 0.55305 | 4.0903 |  |  | Additional application on site | Low
211400 | 211400 | CIS | SG-008 | €21m - Newtow Meadows Development, Phase 4, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6616 | -8.544 | 98 | 50–99 | Mixed | Standard planning application | Private | Private | Commencement Expected | Under construction | 2021-10-08 | 2022-06-09 | Yes | No | 2027-06-08 | 2024-07-01 | Commencement notice | 1 | 8 |  | 4 | 4 | 0.66804 | 2.0616 |  |  | Additional application on site | Low
191236 | 191236 | CIS | SG-008 | €16m - Housing Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6632 | -8.5466 | 92 | 50–99 | Apartments | Standard planning application | Private | Private | Complete | Complete | 2019-12-12 | 2021-03-04 | Yes | No | 2026-03-03 | 2022-11-01 | Commencement notice | 5 | 70 | 2026-05-15 | 11 | 23 | 1.2266 | 1.6619 | 3.5346 | 26.0287 | Additional application on site | Low |  | CIS
19547 | 19547 | CIS | SG-008 | €18m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6618 | -8.5431 | 90 | 50–99 | Apartments | Standard planning application | Private | Private | Commencement Expected | Under construction | 2019-06-06 | 2020-05-28 | Yes | Yes | 2025-05-27 | 2022-05-26 | Commencement notice | 5 | 62 |  | 8 | 13 | 0.97741 | 1.9932 |  |  | Additional application on site | Low
2560399 | 2560399 | CIS | P-1402906 | €16.4m - Residential Development | Annacotty | Limerick City East | Castletroy/Annacotty | 52.6657 | -8.5339 | 76 | 50–99 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-05-02 | 2026-07-13 | Yes | Yes | 2031-07-12 |  |  | 1 | 11 |  | 0 | 0 | 1.1964 |  |  |  | Primary | High
2360866 | 2360866 | CIS | P-1320420 | €16.8m - Residential Development, Castleconnell | Castleconnell | Limerick City East | Outside city neighbourhoods | 52.7112 | -8.4953 | 74 | 50–99 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2023-11-24 | 2024-06-12 | Yes | No | 2029-06-11 | 2024-12-31 | Commencement notice | 3 | 58 |  | 0 | 0 | 0.55031 | 0.55305 |  |  | Primary | High
201074 | 201074 | CIS | P-1129627 | €13m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6614 | -8.5734 | 62 | 50–99 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2020-10-22 | 2021-05-06 | Yes | No | 2026-05-05 | 2023-06-01 | Commencement notice | 6 | 63 |  | 7 | 14 | 0.53662 | 2.0698 |  |  | Primary | High
21350 | 21350 | CIS | SG-008 | €14m - Residential Development,Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6608 | -8.5467 | 62 | 50–99 | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2021-03-22 | 2021-12-03 | Yes | No | 2026-12-02 | 2022-03-25 | Commencement notice | 2 | 24 |  | 6 | 11 | 0.70089 | 0.30664 |  |  | Replaces earlier | Medium
258328 | 258328 | CIS | U-1425841 | €14m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City East | Southhill | 52.6473 | -8.6222 | 57 | 50–99 | Mixed | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2025-12-19 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
21580 | 21580 | CIS | U-1164424 | €9.6m - Residential Development | Limerick City and Suburbs | Limerick City East | Singland/Garryowen | 52.6614 | -8.5994 | 55 | 50–99 | Mixed | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2021-04-30 | 2025-05-13 | Yes | Yes | 2030-05-12 |  |  | 0 | 0 |  | 0 | 0 | 4.0356 |  |  |  | Primary | High
187031 | 187031 | CIS | SG-009 | €11m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6671 | -8.5442 | 54 | 50–99 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2018-08-29 | 2018-10-23 | No | No | 2021-12-31 | 2021-04-12 | CIS start date | 0 | 0 |  | 0 | 0 | 0.15058 | 2.4695 |  |  | Extension of duration (parent not in CIS) | Low
181243 | 181243 | CIS | SG-007 | €6.4m - Residential Development, Crossagalla | Kilmallock | Limerick City East | Southhill | 52.645 | -8.5838 | 53 | 50–99 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-12-19 | 2019-09-04 | Yes | No | 2024-09-03 | 2021-04-28 | Commencement notice | 3 | 53 | 2024-04-10 | 28 | 50 | 0.7091 | 1.6482 | 2.9514 | 17.9576 | Additional application on site | Low |  | CIS
19518 | 19518 | CIS | SG-010 | €11m - Mixed Use Development, Castleconnell | Castleconnell | Limerick City East | Outside city neighbourhoods | 52.7105 | -8.5017 | 51 | 50–99 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2019-05-28 | 2020-12-21 | Yes | Yes | 2025-12-20 | 2022-01-14 | Commencement notice | 1 | 51 |  | 7 | 17 | 1.5688 | 1.065 |  |  | Primary | High
22950 | 22950 | CIS | P-1247398 | €13.9m - Lidl Mixed Use Development , Ballysimon | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6554 | -8.5791 | 48 | 25–49 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2022-08-31 | 2023-09-05 | Yes | No | 2028-09-04 | 2024-07-15 | Commencement notice | 2 | 0 |  | 1 | 1 | 1.013 | 0.85969 |  |  | Primary | High
188007 | 188007 | CIS | P-998747 | €8.9m - Residential Development | Other County Limerick | Limerick City East | Southhill | 52.6462 | -8.6266 | 43 | 25–49 | Houses | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-06-28 | 2018-09-12 | No | No |  | 2020-04-30 | Commencement notice | 4 | 37 | 2021-09-18 | 6 | 7 | 0.20808 | 1.6318 | 1.3854 | 31.039 | Primary | High |  | CIS
18698 | 18698 | CIS | SG-008 | €4.6m - Residential Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6622 | -8.5494 | 38 | 25–49 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-07-06 | 2018-11-21 | Yes | No | 2029-01-23 | 2019-09-18 | Commencement notice | 2 | 38 | 2021-02-10 | 7 | 14 | 0.37782 | 0.82409 | 1.399 | 27.1614 | Primary | High |  | CIS
181270 | 181270 | CIS | SG-005 | €5.8m - Housing Development | Other County Limerick | Limerick City East | Southhill | 52.6572 | -8.585 | 37 | 25–49 | Mixed | Standard planning application | Public – approved housing body | Public | Complete | Complete | 2018-12-20 | 2019-05-29 | Yes | No | 2024-05-28 | 2021-05-25 | Commencement notice | 3 | 31 | 2022-11-15 | 4 | 9 | 0.43806 | 1.9904 | 1.4757 | 25.0728 | Additional application on site | Low |  | Department social housing report | 1682 | CALF Turnkey | Completed | Q4-2022 | Turnkey
1855 | 1855 | CIS | SG-002 | €4.8m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6629 | -8.566 | 32 | 25–49 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2018-01-23 | 2018-07-04 | Yes | No | 2023-07-03 | 2018-08-08 | Commencement notice | 8 | 79 |  | 29 | 31 | 0.44353 | 0.095825 |  |  | Primary | High
2560151 | 2560151 | CIS | U-1391659 | €6.2m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City East | Singland/Garryowen | 52.6569 | -8.5895 | 31 | 25–49 | Mixed | Standard planning application | Private | Private | Contract Awarded | Under construction | 2025-02-24 | 2025-11-27 | Yes | No | 2030-11-26 | 2026-05-12 | Commencement notice | 3 | 31 |  | 0 | 0 | 0.75565 | 0.45448 |  |  | Primary | High
181105 | 181105 | CIS | SG-008 | €2.3m - Housing Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6627 | -8.5485 | 23 | 10–24 | Apartments | Standard planning application | Private | Private | Part Complete | Under construction | 2018-11-14 | 2019-09-19 | Yes | Yes | 2024-09-18 | 2023-07-06 | Commencement notice | 5 | 82 |  | 9 | 43 | 0.846 | 3.7947 |  |  | Additional application on site | Low
211475 | 211475 | CIS | SG-019 | €4.9m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6654 | -8.5472 | 23 | 10–24 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2021-10-22 | 2022-05-03 | Yes | No | 2027-05-02 | 2022-08-15 | Commencement notice | 1 | 23 |  | 1 | 5 | 0.52841 | 0.28474 |  |  | Additional application on site | Low
201320 | 201320 | CIS | SG-009 | €3.7m - Residential Development, Newcastle | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6665 | -8.5444 | 21 | 10–24 | Unknown | Standard planning application | Private | Private | Complete | Complete | 2020-12-10 | 2021-04-27 | Yes | No | 2026-04-26 | 2022-01-26 | Commencement notice | 1 | 21 | 2022-11-30 | 2 | 14 | 0.37782 | 0.75017 | 0.84326 | 24.9034 | Additional application on site | Low |  | CIS
211257 | 211257 | CIS | P-1188558 | €1.8m - Social Housing Development, Limerick | Limerick City and Suburbs | Limerick City East | Singland/Garryowen | 52.6547 | -8.6021 | 15 | 10–24 | Apartments | Standard planning application | Public – approved housing body | Public | Complete | Complete | 2021-09-09 | 2023-09-25 | Yes | Yes | 2028-09-24 | 2024-02-21 | Commencement notice | 1 | 15 | 2025-06-09 | 1 | 15 | 2.0424 | 0.40794 | 1.2977 | 11.5585 | Primary | High |  | CIS | 1680 | CALF Turnkey | Completed | Q4-2025 | Turnkey
2360263 | 2360263 | CIS | P-1286254 | €3.8m - Housing Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6649 | -8.5585 | 14 | 10–24 | Houses | Standard planning application | Private | Private | Part Complete | Under construction | 2023-04-25 | 2023-10-24 | Yes | No | 2028-10-23 | 2024-02-26 | Commencement notice | 1 | 13 |  | 2 | 1 | 0.49829 | 0.34223 |  |  | Primary | High
Part 8 - 1363543 | Part 8 - 1363543 | CIS | P-1363543 | €4m - Housing Development | Other County Limerick | Limerick City East | Southhill | 52.6455 | -8.6158 | 14 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2024-01-01 | 2024-05-01 | No | No |  | 2024-08-23 | CIS start date | 0 | 0 | 2026-03-25 | 0 | 0 | 0.33128 | 0.31211 | 1.5852 | 8.8316 | Primary | High |  | CIS
2460030 | 2460030 | CIS | SG-010 | €2.9m - Residential Development | Castleconnell | Limerick City East | Outside city neighbourhoods | 52.7091 | -8.5027 | 14 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-01-18 | 2025-03-12 | Yes | Yes | 2030-03-11 |  |  | 0 | 0 |  | 0 | 0 | 1.1472 |  |  |  | Additional application on site | Low
22394 | 22394 | CIS | P-1223809 | €2.9m - Housing Development, Castleconnell | Other County Limerick | Limerick City East | Outside city neighbourhoods | 52.713 | -8.4961 | 13 | 10–24 | Houses | Standard planning application | Private | Private | Complete | Complete | 2022-04-07 | 2022-10-27 | Yes | No | 2027-10-26 | 2022-12-07 | Commencement notice | 1 | 13 | 2023-11-30 | 4 | 13 | 0.55578 | 0.11225 | 0.98015 | 13.2633 | Primary | High |  | CIS
178017 | 178017 | Register only (Part 8, not in CIS) |  | Part 8: (a) Provision of 13 no. residential terraced units (11 no. two storey | Limerick City and Suburbs | Limerick City East | City Centre | 52.6543 | -8.6179 | 13 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | Commenced (building control) | Under construction | 2017-12-13 |  | No | No |  | 2019-05-15 | Commencement notice | 1 | 13 |  | 1 | 6 |  |  |  |  | Primary
198009 | 198009 | CIS | P-1071780 | €1.8m - Housing Development | Other County Limerick | Limerick City East | Outside city neighbourhoods | 52.7509 | -8.4934 | 12 | 10–24 | Houses | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2019-10-14 | 2019-12-12 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.16153 |  |  |  | Primary | High
18496 | 18496 | CIS | P-991834 | €1.3m - Housing Development | Annacotty | Limerick City East | Castletroy/Annacotty | 52.6597 | -8.5387 | 12 | 10–24 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-05-21 | 2019-01-22 | Yes | No | 2024-01-21 | 2019-08-12 | Commencement notice | 2 | 12 | 2021-05-28 | 6 | 12 | 0.67351 | 0.55305 | 1.7933 | 6.6916 | Primary | High |  | CIS
2460468 | 2460468 | CIS | SG-007 | €3.6m - Housing/Creche Development, Crossagalla | Kilmallock | Limerick City East | Southhill | 52.6441 | -8.5879 | 12 | 10–24 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2024-05-17 | 2024-10-24 | Yes | No | 2029-10-23 | 2025-01-08 | Commencement notice | 1 | 12 |  | 0 | 0 | 0.43806 | 0.20808 |  |  | Additional application on site | Low
197025 | 197025 | CIS | SG-014 | Housing Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6553 | -8.567 | 12 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2019-11-06 | 2020-02-07 | Yes | No | 2024-12-01 |  |  | 0 | 0 |  | 0 | 0 | 0.25462 |  |  |  | Extension of duration (parent not in CIS) | Low
|  | CIS | U-1419395 | €2.1m - Part 8 Residential Development, Limerick | Kilmallock | Limerick City East | Southhill | 52.6489 | -8.5979 | 12 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2025-12-15 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1843 | SHIP LA Construction | Stage 2 Pre-Planning | Q2-2025 | Construction
188010 | 188010 | CIS | P-999958 | €2.2m - Residential Development | Other County Limerick | Limerick City East | City Centre | 52.6562 | -8.623 | 11 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-07-09 | 2018-08-31 | No | No |  | 2020-02-13 | Commencement notice | 1 | 11 | 2021-02-24 | 1 | 1 | 0.14511 | 1.4538 | 1.0322 | 10.6572 | Primary | High |  | CIS
2560778 | 2560778 | CIS | U-1412257 | €1.2m - 10 Houses, Crossagalla | Kilmallock | Limerick City East | Southhill | 52.6503 | -8.5997 | 10 | 10–24 | Houses | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2025-08-07 | 2026-02-24 | Yes | No | 2031-02-23 |  |  | 0 | 0 |  | 0 | 0 | 0.55031 |  |  |  | Primary | High
191037 | 191037 | CIS | SG-014 | €2.3m - 8 Residential Units | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6536 | -8.5652 | 8 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2019-10-18 | 2020-10-13 | Yes | Yes | 2025-10-12 | 2024-04-18 | Commencement notice | 1 | 6 |  | 0 | 0 | 0.98836 | 3.5127 |  |  | Primary | High
248132 | 248132 | CIS | P-1360553 | €1.4m - 6 Houses, Annacotty | Annacotty | Limerick City East | Castletroy/Annacotty | 52.6689 | -8.5314 | 6 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2024-08-06 | 2024-12-04 | No | No |  | 2026-05-13 | Commencement notice | 1 | 6 |  | 0 | 0 | 0.32854 | 1.4374 |  |  | Primary | High |  |  | 1839 | SHIP LA Construction | Stage 4 Tender Report / Final Turnkey or CALF Approval | Q1-2026 | Construction
187020 | 187020 | CIS | P-997576 | €1m - Residential Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6597 | -8.5496 | 6 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-06-20 | 2018-08-08 | No | No | 2023-05-13 | 2019-04-05 | Commencement notice | 1 | 6 | 2020-03-27 | 3 | 6 | 0.13415 | 0.65708 | 0.97741 | 6.1387 | Extension of duration (parent not in CIS) | Low |  | CIS
PT8LL277 | PT8LL277 | CIS | U-1412368 | €1.5m - 5 Residential Units, Limerick | Limerick City and Suburbs | Limerick City East | Southhill | 52.652 | -8.6102 | 5 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Tender | Not started – permission live | 2025-08-05 | 2025-12-15 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.3614 |  |  |  | Primary | High |  |  | 1846 | SHIP LA Construction | Stage 2 Pre-Planning | Q3-2025 | Construction
178015 | 178015 | Register only (Part 8, not in CIS) |  | Part 8: provision of 5 no. residential terraced units (all two storey) and all | Limerick City and Suburbs | Limerick City East | Southhill | 52.6481 | -8.626 | 5 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Commenced (building control) | Under construction | 2017-10-27 |  | No | No |  | 2019-01-07 | Commencement notice | 1 | 5 |  | 1 | 1 |  |  |  |  | Primary
1872 | 1872 | CIS | P-974045 | €554k - 4 Houses | Other County Limerick | Limerick City East | Southhill | 52.6564 | -8.5876 | 4 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-01-30 | 2019-01-18 | Yes | No | 2024-01-17 | 2020-08-07 | Commencement notice | 1 | 4 | 2023-06-16 | 1 | 4 | 0.96646 | 1.5524 | 2.8556 | 1.4008 | Primary | High |  | CIS
18618 | 18618 | CIS | SG-007 | €529k - 4 Houses | Kilmallock | Limerick City East | Southhill | 52.6445 | -8.588 | 4 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Under construction | 2018-06-21 | 2018-11-27 | Yes | No | 2023-11-26 | 2019-07-19 | Commencement notice | 1 | 20 |  | 20 | 20 | 0.43532 | 0.64066 |  |  | Primary | High
2561323 | 2561323 | CIS | SG-019 | €757k - 4 Apartments, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6692 | -8.5524 | 4 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-12-12 | 2026-07-30 | Yes | No | 2031-07-30 |  |  | 0 | 0 |  | 0 | 0 | 0.62971 |  |  |  | Additional application on site | Low
Part 8 / 1033981 | 188003 | CIS | U-1033981 | €960k - Residential Development | Castleconnell | Limerick City East | Outside city neighbourhoods | 52.7045 | -8.5059 | 4 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Tender | Under construction | 2018-04-16 | 2018-06-13 | No | No |  | 2019-08-27 | Commencement notice | 1 | 4 |  | 1 | 3 | 0.1588 | 1.2047 |  |  | Primary | High
Part 8 - 1378081 | Part 8 - 1378081 | CIS | U-1378081 | €879k - 4 Houses | Limerick City and Suburbs | Limerick City East | Southhill | 52.6447 | -8.6173 | 4 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2024-11-16 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2660652 | 2660652 | CIS | U-1442414 | €540k - 4 Apartments, Limerick | Limerick City and Suburbs | Limerick City East | City Centre | 52.6606 | -8.624 | 4 | 1–9 | Apartments | Standard planning application | Private | Private | Plans Submitted | In planning | 2026-06-12 |  | Yes | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2360493 | 2360493 | CIS | P-1299520 | €1.4m - 3 Houses | Other County Limerick | Limerick City East | Outside city neighbourhoods | 52.6083 | -8.6241 | 3 | 1–9 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2023-07-13 | 2024-01-02 | Yes | No | 2029-01-01 | 2024-04-01 | Commencement notice | 3 | 3 |  | 0 | 0 | 0.47365 | 0.24641 |  |  | Primary | High
20361 | 20361 | CIS | SG-002 | €648k - 3 Houses | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.6642 | -8.5681 | 3 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2020-05-06 | 2021-06-15 | Yes | No | 2026-06-14 | 2022-09-26 | Commencement notice | 1 | 1 |  | 1 | 1 | 1.1088 | 1.2813 |  |  | Additional application on site | Low
21853 | 21853 | CIS | SG-002 | €622k - 2 Houses | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | 52.665 | -8.5669 | 2 | 1–9 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2021-06-16 | 2021-12-15 | Yes | No | 2026-12-14 | 2023-09-25 | Commencement notice | 1 | 1 |  | 0 | 0 | 0.49829 | 1.7769 |  |  | Additional application on site | Low
23557 | 23557 | CIS | SG-024 | €33m - LRD Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.6674 | -8.6492 | 167 | 100+ | Apartments | LRD | Private | Private | On Site | Under construction | 2023-11-17 | 2024-08-23 | Yes | Yes | 2029-08-22 | 2025-09-04 | Commencement notice | 12 | 376 |  | 0 | 0 | 0.7666 | 1.0322 |  |  | Additional phase | Medium
ABPREF312683 | ABPREF312683 | CIS | P-1214059 | €27.5m - Clonmacken Gardens Housing Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.6621 | -8.6689 | 165 | 100+ | Mixed | SHD (An Bord Pleanála) | Private | Private | Permission Granted | Not started – permission live | 2022-02-09 | 2022-05-26 | No | No | 2027-05-25 |  |  | 0 | 0 |  | 0 | 0 | 0.29021 |  |  |  | Primary | High
2360951 | 2360951 | CIS | P-1325143 | €28m - Mixed Use Development, Moyross | Other County Limerick | Limerick City North | Caherdavin | 52.6844 | -8.655 | 115 | 100+ | Mixed | Standard planning application | Public – approved housing body | Public | On Site | Under construction | 2023-12-20 | 2024-03-27 | No | No | 2029-03-26 | 2026-06-04 | Commencement notice | 1 | 73 |  | 0 | 0 | 0.26831 | 2.1875 |  |  | Primary | High
211800 | 211800 | CIS | SG-027 | €21m - Residential Development, Old Cratloe Road | Other County Limerick | Limerick City North | Caherdavin | 52.6834 | -8.6668 | 99 | 50–99 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2021-12-22 | 2024-04-08 | Yes | Yes | 2029-04-07 |  |  | 0 | 0 |  | 0 | 0 | 2.2943 |  |  |  | Primary | High
2460032 | 2460032 | CIS | SG-027 | €18.9m - Residential Development, Old Cratloe Road | Other County Limerick | Limerick City North | Caherdavin | 52.6814 | -8.6684 | 99 | 50–99 | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2024-01-18 | 2024-08-20 | Yes | No | 2029-08-19 | 2025-08-20 | Commencement notice | 4 | 182 |  | 0 | 0 | 0.58864 | 0.99932 |  |  | Additional application on site | Low
22959 | 22959 | CIS | SG-027 | €20m - Residential Development, Limerick. | Other County Limerick | Limerick City North | Caherdavin | 52.6847 | -8.6678 | 98 | 50–99 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-09-05 | 2024-11-21 | Yes | Yes | 2029-11-20 |  |  | 0 | 0 |  | 0 | 0 | 2.2122 |  |  |  | Additional application on site | Low
19970 | 19970 | CIS | SG-012 | €16m - Residential Development, Ennis Road | Other County Limerick | Limerick City North | Caherdavin | 52.6721 | -8.6722 | 92 | 50–99 | Mixed | Standard planning application | Private | Private | Commencement Expected | Under construction | 2019-10-01 | 2020-11-16 | Yes | Yes | 2028-11-14 | 2023-04-10 | Commencement notice | 3 | 48 |  | 8 | 7 | 1.128 | 2.3956 |  |  | Primary | High
22817 | 22817 | CIS | P-1242233 | €11m - Residential Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.6823 | -8.664 | 86 | 50–99 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-07-25 | 2023-07-04 | Yes | No | 2028-07-03 |  |  | 0 | 0 |  | 0 | 0 | 0.94182 |  |  |  | Primary | High
217025 | 217025 | CIS | SG-024 | €3.7m - Ardhú Apartments Refurbishment, Ennis Road | Other County Limerick | Limerick City North | Caherdavin | 52.6668 | -8.6499 | 65 | 50–99 | Mixed | Standard planning application | Private | Private | Complete | Complete | 2021-06-01 | 2021-07-14 | No | No | 2026-11-19 | 2022-08-29 | Commencement notice | 1 | 56 | 2023-12-13 | 1 | 1 | 0.11773 | 1.1253 | 1.2895 | 50.4061 | Extension of duration (parent not in CIS) | Low |  | CIS
221114 | 221114 | CIS | SG-027 | €12.2m - Residential Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.6841 | -8.6698 | 54 | 50–99 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-10-17 | 2024-10-18 | Yes | Yes | 2029-10-17 |  |  | 0 | 0 |  | 0 | 0 | 2.0041 |  |  |  | Additional application on site | Low
221400 | 221400 | CIS | P-1265188 | €10.4m - Residential Development, Thomondgate | Other County Limerick | Limerick City North | Caherdavin | 52.675 | -8.6328 | 46 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-12-30 | 2024-07-26 | Yes | Yes | 2029-07-25 |  |  | 0 | 0 |  | 0 | 0 | 1.5715 |  |  |  | Primary | High
188008 | 188008 | CIS | P-999956 | €7m - Residential Development, Condell Road | Other County Limerick | Limerick City North | Caherdavin | 52.6615 | -8.6662 | 43 | 25–49 | Houses | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-07-05 | 2018-09-12 | No | No |  | 2019-09-24 | Commencement notice | 1 | 43 | 2024-12-20 | 1 | 1 | 0.18891 | 1.0322 | 5.2402 | 8.2057 | Primary | High |  | CIS | 1817 | SHIP LA Construction | Completed | Q4-2024 | Construction
Part 8 - 1063948 | Part 8 - 1063948 | CIS | P-1063948 | €9m - Rapid Housing Delivery | Other County Limerick | Limerick City North | Caherdavin | 52.681 | -8.6506 | 38 | 25–49 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2019-08-19 | 2019-12-06 | No | No |  | 2021-04-22 | CIS start date | 0 | 0 |  | 0 | 0 | 0.29843 | 1.3771 |  |  | Primary | High
19710 | 19710 | CIS | P-1058796 | €8.5m - Student Accommodation Development, Former Hassett’s Bar | Other County Limerick | Limerick City North | Caherdavin | 52.6729 | -8.6399 | 31 | 25–49 | Student | Standard planning application | Private | Private | Stalled or Suspended | Not started – permission live | 2019-07-18 | 2021-03-15 | Yes | Yes | 2029-03-13 |  |  | 0 | 0 |  | 0 | 0 | 1.6591 |  |  |  | Primary | High | On hold / no movement
211640 | 211640 | CIS | P-1202244 | €3.8m - Residential Development, Curry Lane | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6659 | -8.6194 | 30 | 25–49 | Apartments | Standard planning application | Public – approved housing body | Public | Commencement Expected | Under construction | 2021-11-29 | 2022-03-08 | No | No | 2027-03-07 | 2024-07-11 | Commencement notice | 1 | 1 |  | 0 | 0 | 0.27105 | 2.3436 |  |  | Primary | High
2560169 | 2560169 | CIS | U-1393371 | €4.8m - Mixed Use Development, Limerick | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6655 | -8.6165 | 30 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-03-05 | 2025-08-13 | Yes | No | 2030-08-12 |  |  | 0 | 0 |  | 0 | 0 | 0.44079 |  |  |  | Additional application on site | Low
258327 | 258327 | CIS | U-1419614 | €4.8m - Apartment Development, Limerick | Limerick City and Suburbs | Limerick City North | Kings Island | 52.6671 | -8.6204 | 30 | 25–49 | Apartments | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2025-12-13 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Additional application on site | Low |  |  | 1837 | SHIP LA Construction | Stage 2 Pre-Planning | Q1-2026 | Construction
221189 | 221189 | CIS | P-1258052 | €6.3m - Apartment Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.672 | -8.638 | 28 | 25–49 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2022-11-07 | 2024-12-19 | Yes | Yes | 2029-12-18 | 2026-02-20 | Commencement notice | 2 | 14 |  | 0 | 0 | 2.1164 | 1.1718 |  |  | Primary | High
198003 | 198003 | CIS | P-1050624 | €3.9m - Residential Development, Moyross | Other County Limerick | Limerick City North | Caherdavin | 52.6788 | -8.64 | 27 | 25–49 | Mixed | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2019-06-05 | 2019-09-10 | No | No |  | 2022-07-18 | Commencement notice | 2 | 27 |  | 2 | 17 | 0.26557 | 2.8528 |  |  | Primary | High
198004 | 198004 | CIS | P-1054214 | €6m - Residential Development, King's Island | Other County Limerick | Limerick City North | Kings Island | 52.6714 | -8.625 | 27 | 25–49 | Apartments | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2019-06-26 | 2019-10-02 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.26831 |  |  |  | Additional application on site | Low
187040 | 187040 | CIS | P-1022341 | €5.7m - Residential Development, Rhebogue | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6645 | -8.5992 | 26 | 25–49 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2018-11-30 | 2018-12-14 | No | No | 2023-12-30 | 2020-10-21 | Commencement notice | 2 | 17 |  | 8 | 17 | 0.03833 | 1.8535 |  |  | Extension of duration (parent not in CIS) | Low
21520 | 21520 | CIS | P-1162677 | €6.5m - Housing Development Limerick | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | 52.6763 | -8.6079 | 26 | 25–49 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2021-04-22 | 2023-12-04 | Yes | Yes | 2028-12-03 | 2024-07-17 | Commencement notice | 3 | 46 |  | 0 | 0 | 2.6174 | 0.61875 |  |  | Primary | High
221216 | 221216 | CIS | P-1259753 | €14m - Old Dublin Road Student Village LRD, Limerick City | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6637 | -8.5906 | 26 | 25–49 | Student | LRD | Private | Private | On Site | Under construction | 2022-11-17 | 2023-05-17 | No | Yes | 2028-05-16 | 2024-12-27 | Commencement notice | 1 | 0 |  | 0 | 0 | 0.49555 | 1.6153 |  |  | Primary | High
2460713 | 2460713 | CIS | P-1357447 | €4.2m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6661 | -8.5996 | 25 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-07-18 | 2025-10-31 | Yes | Yes | 2030-10-30 |  |  | 0 | 0 |  | 0 | 0 | 1.2868 |  |  |  | Primary | High
2560953 | 2560953 | CIS | P-1414128 | €4.8m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | 52.6752 | -8.6163 | 25 | 25–49 | Mixed | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-09-22 | 2026-04-29 | Yes | No | 2031-04-28 |  |  | 0 | 0 |  | 0 | 0 | 0.59959 |  |  |  | Primary | High
187029 | 187029 | CIS | P-1005377 | €1.9m - Housing Development | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | 52.6861 | -8.6198 | 24 | 10–24 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-08-13 | 2018-10-04 | No | No | 2021-12-31 | 2018-03-13 | CIS start date | 0 | 0 | 2025-06-30 | 0 | 0 | 0.14237 |  | 7.2991 | 3.2881 | Extension of duration (parent not in CIS) | Low |  | CIS
|  | CIS | U-1422145 | €719k - Architect Led Integrated Design Team Services for 23 Residential Units, Limerick | Limerick City and Suburbs | Limerick City North | Kings Island | 52.671 | -8.625 | 23 | 10–24 | Unknown | Standard planning application | Public – local authority | Public | Contract Awarded | Not started – permission live |  |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Additional application on site | Low
PT8LL283 | 258283 | CIS | U-1412942 | €5.4m - Cosgrave Park Phase 2, Moyross | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6808 | -8.6428 | 22 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2025-08-25 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1844 | SHIP LA Construction | Stage 2 Pre-Planning | Q2-2025 | Construction
22793 | 22793 | CIS | U-1241529 | €4.5m - Housing Development, Limerick City | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6648 | -8.6088 | 20 | 10–24 | Apartments | Standard planning application | Private | Private | Contract Awarded | Under construction | 2022-07-20 | 2024-02-01 | No | Yes | 2029-01-31 | 2024-12-31 | Commencement notice | 1 | 0 |  | 0 | 0 | 1.5359 | 0.91444 |  |  | Primary | High | On hold / no movement
2460633 | 2460633 | CIS | U-1353358 | €2.7m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City North | City Centre | 52.6626 | -8.6222 | 15 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-06-25 | 2025-04-24 | Yes | No | 2030-04-23 |  |  | 0 | 0 |  | 0 | 0 | 0.82957 |  |  |  | Primary | High
2460864 | 2460864 | CIS | U-1363929 | €4.2m - Residential Development | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | 52.6707 | -8.6046 | 15 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-08-28 | 2025-09-18 | Yes | No | 2030-09-17 |  |  | 0 | 0 |  | 0 | 0 | 1.0568 |  |  |  | Primary | High
188001 | 188001 | CIS | P-1045472 | €3m - Residential Development, Mulgrave Street | Other County Limerick | Limerick City North | City Centre | 52.6579 | -8.6105 | 14 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-02-07 | 2018-05-16 | No | No |  | 2020-02-10 | Commencement notice | 1 | 14 | 2022-02-03 | 1 | 5 | 0.26831 | 1.7385 | 1.9822 | 7.0628 | Primary | High |  | CIS
21835 | 21835 | CIS | SG-025 | €3.5m - Apartment Development, Limerick | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6655 | -8.6165 | 14 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2021-06-14 | 2022-02-17 | Yes | No | 2027-02-16 |  |  | 0 | 0 |  | 0 | 0 | 0.67899 |  |  |  | Primary | High
268371 | 268371 | CIS | U-1431510 | €3.2m - Residential Development, Thomondgate | Limerick City and Suburbs | Limerick City North | City Centre | 52.6736 | -8.6322 | 13 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2026-03-31 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1849 | SHIP LA Construction | Stage 2 Pre-Planning | Q1-2026 | Construction
22917 | 22917 | CIS | SG-027 | €3.6m - Mixed Use Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | 52.682 | -8.6668 | 12 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-08-19 | 2023-10-03 | Yes | No | 2028-10-02 |  |  | 0 | 0 |  | 0 | 0 | 1.1225 |  |  |  | Additional application on site | Low
19302 | 19302 | CIS | U-1040199 | €2.6m - Apartments | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6838 | -8.6495 | 12 | 10–24 | Apartments | Standard planning application | Public – approved housing body | Public | Tender | Not started – past expiry | 2019-03-29 | 2019-06-19 | No | No | 2024-06-18 |  |  | 0 | 0 |  | 0 | 0 | 0.2245 |  |  |  | Primary | High
21147 | 21147 | CIS | SG-021 | €1.4m - Housing Development | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6733 | -8.6578 | 11 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2021-02-12 | 2022-02-07 | Yes | No | 2027-02-06 |  |  | 0 | 0 |  | 0 | 0 | 0.98563 |  |  |  | Primary | High
2360759 | 2360759 | CIS | SG-025 | €1.4m - Retail Units/Apartments | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6668 | -8.6165 | 8 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2023-10-18 | 2024-07-17 | Yes | No | 2029-07-16 |  |  | 0 | 0 |  | 0 | 0 | 0.74743 |  |  |  | Additional application on site | Low
2560001 | 2560001 | CIS | P-1384661 | €1.3m - 6 Apartments, Thomondgate | Other County Limerick | Limerick City North | City Centre | 52.6724 | -8.6308 | 7 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2025-01-03 | 2025-12-03 | Yes | No | 2030-12-02 | 2026-03-16 | Commencement notice | 1 | 1 |  | 0 | 0 | 0.91444 | 0.282 |  |  | Primary | High
178001 | 178001 | Register only (Part 8, not in CIS) |  | Part 8: (1)Provision of 7no. residential units, 2no. two storey and 5no. singl | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6628 | -8.6107 | 7 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Commenced (building control) | Under construction | 2017-03-06 |  | No | No |  | 2018-09-24 | Commencement notice | 1 | 7 |  | 1 | 7 |  |  |  |  | Primary
178012 | 178012 | Register only (Part 8, not in CIS) |  | Part 8: (i) provision of 7 no. residential units (2 no. three-storey, 3 bedroo | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | 52.6664 | -8.6161 | 7 | 1–9 | Apartments | Part 8 / council | Public – local authority | Public | Complete | Complete | 2017-10-16 |  | No | No |  | 2024-12-31 | Commencement notice | 1 | 7 | 2025-11-15 | 1 | 1 |  |  | 0.87337 | 8.0149 | Primary |  |  | Department social housing report | 1820 | SHIP LA Construction | Completed | Q4-2025 | Construction
21342 | 21342 | CIS | P-1156999 | €864k - 6 Dwellings | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6751 | -8.6546 | 6 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2021-03-22 | 2022-04-13 | Yes | No | 2027-04-12 | 2023-03-20 | Commencement notice | 1 | 6 | 2025-10-23 | 1 | 6 | 1.0595 | 0.93361 | 2.5955 | 2.3117 | Primary | High |  | CIS
211395 | 211395 | CIS | P-1193931 | €1.3m - 6 Houses | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6653 | -8.5979 | 6 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2021-10-07 | 2022-06-21 | Yes | No | 2027-06-20 | 2026-02-13 | Commencement notice | 1 | 6 |  | 0 | 0 | 0.70363 | 3.6496 |  |  | Primary | High
CE/2019/087 | CE/2019/087 | CIS | P-1363541 | €1.5m - Housing Development | Other County Limerick | Limerick City North | Caherdavin | 52.6824 | -8.6566 | 6 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2024-01-01 | 2024-05-04 | No | No |  | 2024-08-19 | CIS start date | 0 | 0 | 2025-12-09 | 0 | 0 | 0.33949 | 0.29295 | 1.306 | 4.5943 | Primary | High |  | CIS
268364 | 268364 | CIS | U-1438136 | €883k - Part 8 - 6 Apartments, Corbally | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | 52.6851 | -8.6231 | 6 | 1–9 | Apartments | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2026-03-13 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
268363 | 268363 | CIS | U-1439022 | €1.4m - 6 Houses, Caherdavin | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6732 | -8.6711 | 6 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2026-03-13 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1851 | SHIP LA Construction | Stage 1 Capital Appraisal | Q1-2025 | Construction
248153 | 248153 | CIS | U-1447625 | €1.4m - Part 8 - 2 Houses & 4 Apartments, Thomondghate | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6756 | -8.6336 | 6 | 1–9 | Apartments | Part 8 / council | Public – local authority | Public | Plans Submitted | In planning | 2024-08-29 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Additional application on site | Low |  |  | 1832 | SHIP LA Construction | Stage 3 Pre-Tender Design | Q4-2025 | Construction
188009 | 188009 | CIS | P-999957 | €1.1m - Residential Units | Other County Limerick | Limerick City North | Caherdavin | 52.6748 | -8.6389 | 5 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-07-09 | 2018-08-31 | No | No |  | 2020-07-20 | Commencement notice | 1 | 5 | 2021-04-21 | 1 | 1 | 0.14511 | 1.8864 | 0.75291 | 6.6409 | Primary | High |  | CIS
188004 | 188004 | Register only (Part 8, not in CIS) |  | Part 8: (i) provision of 5 no. residential units (3 no. 2 bedroom houses and 2 | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6725 | -8.6346 | 5 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2018-04-16 | 2018-06-13 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.1588 |  |  |  | Primary
20827 | 20827 | CIS | P-1120093 | €864k - 4 Houses | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6671 | -8.5937 | 4 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-08-25 | 2021-08-26 | Yes | No | 2026-08-25 |  |  | 0 | 0 |  | 0 | 0 | 1.0021 |  |  |  | Primary | High
23283 | 23283 | CIS | P-1292276 | €907k - Change of Use to 4 Apartments | Other County Limerick | Limerick City North | City Centre | 52.6626 | -8.6195 | 4 | 1–9 | Apartments | Standard planning application | Public – approved housing body | Public | Permission Granted | Not started – permission live | 2023-05-31 | 2023-08-16 | No | No | 2028-08-15 |  |  | 0 | 0 |  | 0 | 0 | 0.21081 |  |  |  | Primary | High
198008 | 198008 | Register only (Part 8, not in CIS) |  | Part 8: (a) provision of 3 no. residential two-storey terraced units comprisin | Limerick City and Suburbs | Limerick City North | City Centre | 52.6582 | -8.6106 | 3 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Commenced (building control) | Under construction | 2019-10-14 | 2019-12-12 | No | No |  | 2020-04-21 | Commencement notice | 1 | 3 |  | 1 | 2 | 0.16153 | 0.35866 |  |  | Primary
|  | CIS | U-1417205 | €1.4m - Architect Led Integrated Design Team for College Avenue Infill Housing Scheme, Moyross | Limerick City and Suburbs | Limerick City North | Caherdavin | 52.6802 | -8.6482 | 0 | Unknown | Unknown | Standard planning application | Public – local authority | Public | Contract Awarded | Not started – permission live |  |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2561232 | 2561232 | CIS | P-1417746 | €9.4m - Student Accommodation Development, Limerick | Other County Limerick | Limerick City North | Singland/Garryowen | 52.6645 | -8.6145 |  | Unknown | Student | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-11-25 | 2026-07-28 | Yes | Yes | 2031-07-27 |  |  | 0 | 0 |  | 0 | 0 | 0.67077 |  |  |  | Primary | High
ABPREF313124 | ABPREF313124 | CIS | P-1221693 | €76m - Residential Development, Raheen | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.6398 | -8.6703 | 384 | 100+ | Mixed | SHD (An Bord Pleanála) | Private | Private | Commencement Expected | Under construction | 2022-03-25 | 2022-06-30 | No | No | 2032-06-29 | 2024-04-24 | Commencement notice | 3 | 116 |  | 0 | 0 | 0.26557 | 1.8179 |  |  | Primary | High
ABPREF311588 | ABPREF311588 | CIS | P-1194302 | €66m - Greenpark SHD Residential Development, Dock Road, Limerick | Other County Limerick | Limerick City West | Ballinacurra | 52.6467 | -8.6514 | 371 | 100+ | Mixed | SHD (An Bord Pleanála) | Private | Private | On Site | Under construction | 2021-10-07 | 2022-03-30 | No | No | 2027-03-29 | 2023-07-31 | Commencement notice | 19 | 241 |  | 21 | 38 | 0.47639 | 1.3361 |  |  | Primary | High
2560780 | 2560780 | CIS | U-1412002 | €95m - Dock Road LRD, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | 52.659 | -8.637 | 285 | 100+ | Apartments | LRD | Public – LDA | Public | Tender | Not started – permission live | 2025-08-07 | 2026-02-11 | Yes | No | 2031-02-10 |  |  | 0 | 0 |  | 0 | 0 | 0.51472 |  |  |  | Primary | High
218000 | 218000 | CIS | SG-020 | €47m - The Mungret Project | Mungret | Limerick City West | Dooradoyle | 52.6297 | -8.6774 | 250 | 100+ | Mixed | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2021-02-03 | 2021-07-13 | No | No |  | 2026-07-29 | Commencement notice | 1 | 99 |  | 0 | 0 | 0.43806 | 5.0431 |  |  | Primary | High | On hold / no movement
2660396 | 2660396 | CIS | P-1432711 | €39m - Large Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6312 | -8.6903 | 182 | 100+ | Mixed | LRD | Private | Private | Permission Granted | Not started – permission live | 2026-04-08 | 2026-09-15 | Yes | No | 2031-09-15 |  |  | 0 | 0 |  | 0 | 0 | 0.43806 |  |  |  | Primary | High
2561231 | 2561231 | CIS | SG-020 | €32.5m - Large Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6285 | -8.6785 | 169 | 100+ | Mixed | LRD | Private | Private | Permission Granted | Not started – permission live | 2025-11-25 | 2026-07-30 | Yes | No | 2031-07-30 |  |  | 0 | 0 |  | 0 | 0 | 0.67625 |  |  |  | Additional application on site | Low
2461282 | 2461282 | CIS | P-1382991 | €32m - LRD, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6364 | -8.6975 | 139 | 100+ | Mixed | LRD | Private | Private | Permission Granted | Not started – permission live | 2024-12-19 | 2025-09-24 | Yes | Yes | 2030-09-23 |  |  | 0 | 0 |  | 0 | 0 | 0.76386 |  |  |  | Primary | High
2360703 | 2360703 | CIS | U-1310780 | €27m - Mixed Use Development, Dooradoyle | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.6282 | -8.6636 | 104 | 100+ | Apartments | Standard planning application | Private | Private | Tender | Not started – permission live | 2023-09-25 | 2025-04-14 | Yes | Yes | 2030-04-13 |  |  | 0 | 0 |  | 0 | 0 | 1.5524 |  |  |  | Primary | High
211217 | 211217 | CIS | SG-013 | €15.2m - Residential Development Mungret | Mungret | Limerick City West | Dooradoyle | 52.631 | -8.6737 | 101 | 100+ | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2021-08-30 | 2023-07-28 | Yes | Yes | 2028-07-27 | 2024-02-13 | Commencement notice | 9 | 106 |  | 11 | 12 | 1.9083 | 0.54757 |  |  | Additional application on site | Low
211216 | 211216 | CIS | SG-013 | €21m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6303 | -8.6722 | 99 | 50–99 | Mixed | Standard planning application | Private | Private | Part Complete | Under construction | 2021-08-30 | 2023-07-28 | Yes | Yes | 2028-07-27 | 2024-04-20 | Commencement notice | 7 | 99 |  | 3 | 5 | 1.9083 | 0.73101 |  |  | Additional application on site | Low
201115 | 201115 | CIS | SG-001 | €16.5m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6359 | -8.6793 | 96 | 50–99 | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2020-10-30 | 2021-05-27 | Yes | No | 2029-07-09 | 2026-04-07 | CIS start date | 0 | 0 |  | 0 | 0 | 0.57221 | 4.8624 |  |  | Additional application on site | Low
201114 | 201114 | CIS | SG-001 | €19.4m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6384 | -8.6783 | 96 | 50–99 | Mixed | Standard planning application | Private | Private | Commencement Expected | Under construction | 2020-10-30 | 2021-05-27 | Yes | No | 2026-05-26 | 2022-02-21 | Commencement notice | 1 | 26 |  | 2 | 2 | 0.57221 | 0.73922 |  |  | Additional application on site | Low
2561242 | 2561242 | CIS | SG-017 | €14.5m - Residential Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.6602 | -8.6294 | 76 | 50–99 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-11-28 | 2026-06-10 | Yes | No | 2031-06-09 |  |  | 0 | 0 |  | 0 | 0 | 0.53114 |  |  |  | Additional application on site | Low
2360615 | 2360615 | CIS | P-1306162 | €11.3m - Housing Development, Mungret | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.6359 | -8.6774 | 66 | 50–99 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2023-08-25 | 2024-01-15 | Yes | No | 2029-01-14 | 2024-04-22 | Commencement notice | 4 | 66 |  | 8 | 9 | 0.39151 | 0.26831 |  |  | Primary | High
201195 | 201195 | CIS | SG-013 | €9m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6319 | -8.67 | 66 | 50–99 | Mixed | Standard planning application | Private | Private | Complete | Complete | 2020-11-19 | 2021-06-23 | Yes | No | 2026-06-22 | 2022-04-08 | Commencement notice | 2 | 66 | 2023-11-02 | 5 | 28 | 0.59138 | 0.79124 | 1.5688 | 42.0707 | Additional application on site | Low |  | CIS
2560156 | 2560156 | CIS | SG-004 | €15.9m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6005 | -8.7051 | 63 | 50–99 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-02-25 | 2025-11-11 | Yes | Yes | 2030-11-10 |  |  | 0 | 0 |  | 0 | 0 | 0.7091 |  |  |  | Additional application on site | Low
181193 | 181193 | CIS | SG-003 | €9m - Housing Development | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.5994 | -8.7122 | 58 | 50–99 | Houses | Standard planning application | Private | Private | Part Complete | Under construction | 2018-12-07 | 2019-05-28 | Yes | No | 2027-05-26 | 2024-04-24 | Commencement notice | 2 | 63 |  | 4 | 7 | 0.47091 | 4.909 |  |  | Additional application on site | Low
2561228 | 2561228 | CIS | SG-004 | €18.4m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.602 | -8.6992 | 54 | 50–99 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2025-11-24 | 2026-05-06 | Yes | No | 2031-05-05 | 2026-07-14 | Commencement notice | 1 | 20 |  | 0 | 0 | 0.44627 | 0.18891 |  |  | Additional application on site | Low
221318 | 221318 | CIS | P-1262614 | €10.9m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6029 | -8.7105 | 52 | 50–99 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2022-12-09 | 2023-10-24 | Yes | No | 2028-10-23 | 2025-02-05 | Commencement notice | 1 | 51 |  | 0 | 0 | 0.87337 | 1.2868 |  |  | Primary | High
18200 | 18200 | CIS | SG-003 | €5.9m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.5994 | -8.7098 | 49 | 25–49 | Unknown | Standard planning application | Private | Private | On Site | Under construction | 2018-03-06 | 2018-12-11 | Yes | No | 2026-12-08 | 2022-12-09 | Commencement notice | 3 | 48 |  | 11 | 11 | 0.7666 | 3.9945 |  |  | Primary | High
18346 | 18346 | CIS | SG-004 | €6.3m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6017 | -8.7058 | 49 | 25–49 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2018-04-11 | 2018-10-23 | Yes | No | 2023-10-22 |  |  | 0 | 0 |  | 0 | 0 | 0.53388 |  |  |  | Primary | High | Permission expiring
2560540 | 2560540 | CIS | U-1408292 | €7m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | 52.6575 | -8.6356 | 48 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-06-07 | 2025-11-10 | Yes | No | 2030-11-09 |  |  | 0 | 0 |  | 0 | 0 | 0.4271 |  |  |  | Primary | High
2360144 | 2360144 | CIS | U-1277663 | €9m - Housing Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6009 | -8.7117 | 41 | 25–49 | Houses | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2023-03-13 | 2023-11-15 | Yes | No | 2028-11-14 |  |  | 0 | 0 |  | 0 | 0 | 0.67625 |  |  |  | Additional application on site | Low
2460570 | 2460570 | CIS | P-1350852 | €4.5m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | 52.6648 | -8.6203 | 40 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-06-09 | 2025-02-06 | Yes | No | 2030-02-05 |  |  | 0 | 0 |  | 0 | 0 | 0.66256 |  |  |  | Primary | High
2560653 | 2560653 | CIS | SG-004 | €9.4m - Residential Development | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6019 | -8.7075 | 40 | 25–49 | Houses | Standard planning application | Private | Private | Stalled or Suspended | Not started – permission live | 2025-07-03 | 2026-01-20 | Yes | No | 2031-01-19 |  |  | 0 | 0 |  | 0 | 0 | 0.55031 |  |  |  | Additional application on site | Low | On hold / no movement
211598 | 211598 | CIS | SG-026 | €5.8m - Apartment/Retail Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.6598 | -8.6252 | 37 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2021-11-18 | 2022-05-25 | Yes | No | 2027-05-24 |  |  | 0 | 0 |  | 0 | 0 | 0.51472 |  |  |  | Primary | High
2560546 | 2560546 | CIS | SG-026 | €7m - Residential/Commercial Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.6598 | -8.6252 | 37 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-06-10 | 2025-09-04 | No | No | 2030-09-03 |  |  | 0 | 0 |  | 0 | 0 | 0.23546 |  |  |  | Additional application on site | Low
20281 | 20281 | CIS | SG-004 | €12m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6023 | -8.6997 | 36 | 25–49 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2020-04-02 | 2021-01-15 | Yes | No | 2025-12-01 | 2023-06-09 | Commencement notice | 2 | 50 |  | 0 | 0 | 0.7885 | 2.3956 |  |  | Additional application on site | Low
228016 | 228016 | CIS | SG-029 | €6m - Apartment Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.6571 | -8.6258 | 36 | 25–49 | Apartments | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2022-08-19 | 2022-11-21 | No | No |  | 2024-09-25 | Commencement notice | 1 | 36 |  | 0 | 0 | 0.25736 | 1.8453 |  |  | Additional application on site | Low
191060 | 191060 | CIS | P-895586 | €50m - 1 BQ Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | 52.6625 | -8.6312 | 35 | 25–49 | Unknown | Standard planning application | Private | Private | Complete | Complete | 2019-10-25 | 2020-03-04 | Yes | No | 2022-06-18 | 2022-06-20 | Commencement notice | 1 | 34 | 2024-06-05 | 1 | 1 | 0.35866 | 2.2943 | 1.9603 | 17.8544 | Primary | High | On hold / no movement | CIS
221107 | 221107 | CIS | U-1254537 | €5m - Apartment/Retail Development, Dooradoyle | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.64 | -8.6505 | 30 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-10-14 | 2023-06-14 | Yes | No | 2028-06-13 |  |  | 0 | 0 |  | 0 | 0 | 0.6653 |  |  |  | Primary | High
20467 | 20467 | CIS | SG-006 | €5.4m - Patricks Well Housing Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.636 | -8.6748 | 29 | 25–49 | Mixed | Standard planning application | Private | Private | On Site | Under construction | 2020-06-05 | 2021-01-29 | Yes | No | 2029-03-12 | 2021-10-11 | Commencement notice | 1 | 17 |  | 2 | 13 | 0.65161 | 0.69815 |  |  | Additional phase | Low
221003 | 221003 | CIS | U-1250272 | €6.5m - Apartment Development, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | 52.6593 | -8.6354 | 29 | 25–49 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-09-15 | 2023-07-12 | Yes | No | 2028-07-11 |  |  | 0 | 0 |  | 0 | 0 | 0.82136 |  |  |  | Additional application on site | Low
221172 | 221172 | CIS | P-1256924 | €5.9m - Student Accommodation Development | Other County Limerick | Limerick City West | City Centre | 52.659 | -8.6257 | 25 | 25–49 | Student | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-11-01 | 2024-05-30 | Yes | Yes | 2029-05-29 |  |  | 0 | 0 |  | 0 | 0 | 1.577 |  |  |  | Additional application on site | Low
18465 | 18465 | CIS | SG-006 | €3.4m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6367 | -8.6763 | 25 | 25–49 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-05-11 | 2018-09-18 | Yes | No | 2023-09-17 | 2020-07-16 | Commencement notice | 1 | 19 | 2021-12-15 | 2 | 6 | 0.35592 | 1.8261 | 1.4155 | 17.662 | Additional phase | Low |  | CIS
228017 | 228017 | CIS | SG-004 | €4.4m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6013 | -8.708 | 24 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2022-09-05 | 2022-12-12 | No | No |  | 2026-07-17 | Commencement notice | 1 | 24 |  | 0 | 0 | 0.26831 | 3.5948 |  |  | Additional application on site | Low
Part 8 - 1248404 | Part 8 - 1248404 | CIS | SG-004 | €4.6m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.5982 | -8.7069 | 24 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2022-09-05 | 2023-01-24 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.38604 |  |  |  | Additional application on site | Low
20222 | 20222 | CIS | SG-017 | €8.9m - Mixed Use Development, 34-41 Catherine Street | Other County Limerick | Limerick City West | City Centre | 52.6602 | -8.6292 | 24 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-03-13 | 2021-01-06 | Yes | No | 2026-01-05 |  |  | 0 | 0 |  | 0 | 0 | 0.81862 |  |  |  | Primary | High
221367 | 221367 | CIS | SG-031 | €5.2m - Residential Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.661 | -8.6304 | 24 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-12-19 | 2023-09-13 | Yes | No | 2028-09-12 |  |  | 0 | 0 |  | 0 | 0 | 0.73374 |  |  |  | Primary | High | Site for sale / sold
2560425 | 2560425 | CIS | SG-035 | €4.4m - Apartment Development | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.6258 | -8.6538 | 24 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-05-09 | 2026-04-14 | Yes | Yes | 2031-04-13 |  |  | 0 | 0 |  | 0 | 0 | 0.93087 |  |  |  | Additional application on site | Low
2360150 | 2360150 | CIS | U-1278374 | €3m - Apartment Development, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | 52.658 | -8.6314 | 24 | 10–24 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2023-03-16 | 2023-08-22 | Yes | No | 2028-08-21 | 2025-12-01 | Commencement notice | 1 | 24 |  | 0 | 0 | 0.43532 | 2.2779 |  |  | Primary | High
188012 | 188012 | Register only (Part 8, not in CIS) |  | Part 8: (a) provision of 24 no. two storey residential housing units. The unit | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6012 | -8.7082 | 24 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2018-08-07 | 2018-10-11 | No | No |  |  | Department social housing report (on site by Q3-2023) | 0 | 0 |  | 0 | 0 | 0.17796 |  |  |  | Primary |  |  |  | 1822 | SHIP LA Construction | On Site | Q3-2023 | Construction
2560771 | 2560771 | CIS | P-1411773 | €4.5m - Mixed Use Development | Limerick City and Suburbs | Limerick City West | City Centre | 52.6653 | -8.6226 | 22 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-08-05 | 2026-06-08 | Yes | No | 2031-06-07 |  |  | 0 | 0 |  | 0 | 0 | 0.84052 |  |  |  | Additional application on site | Low
2360345 | 2360345 | CIS | P-1290708 | €3.7m - Residential Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | 52.659 | -8.6271 | 21 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2023-05-23 | 2024-07-09 | No | Yes | 2029-07-08 |  |  | 0 | 0 |  | 0 | 0 | 1.1307 |  |  |  | Additional application on site | Low
2360025 | 2360025 | CIS | SG-028 | €3.8m - Apartment Development, Limerick | Other County Limerick | Limerick City West | Ballinacurra | 52.6479 | -8.6331 | 21 | 10–24 | Apartments | Standard planning application | Public – approved housing body | Public | On Site | Under construction | 2023-01-26 | 2024-08-28 | No | Yes | 2029-08-27 | 2025-10-23 | Commencement notice | 1 | 19 |  | 0 | 0 | 1.588 | 1.1526 |  |  | Primary | High |  |  | 1695 | CALF Turnkey | On Site | Q4-2025 | Turnkey
22471 | 22471 | CIS | U-1227182 | €4.5m - Housing Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6329 | -8.6983 | 21 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2022-04-27 | 2024-01-22 | No | Yes | 2029-01-21 |  |  | 0 | 0 |  | 0 | 0 | 1.7385 |  |  |  | Primary | High
Part 8 - 1371977 | Part 8 - 1371977 | CIS | SG-035 | €3.4m - Residential Development | Limerick City and Suburbs | Limerick City West | Dooradoyle | 52.6241 | -8.6519 | 20 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2024-10-14 | 2025-01-20 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.26831 |  |  |  | Replaces earlier | Medium
|  | CIS | P-1015929 | €2m - Housing Development | Other County Limerick | Limerick City West | Outside city neighbourhoods | 52.6343 | -8.7323 | 17 | 10–24 | Unknown | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2018-10-25 | 2019-09-27 | No | No | 2024-09-27 |  |  | 0 | 0 |  | 0 | 0 | 0.92266 |  |  |  | Primary | High
188014 | 188014 | CIS | P-1015932 | €1.7m - Residential Development, Rosbrien Road | Other County Limerick | Limerick City West | Ballinacurra | 52.6492 | -8.6337 | 17 | 10–24 | Mixed | Part 8 / council | Public – local authority | Public | Complete | Complete | 2018-10-22 | 2018-12-11 | No | No |  | 2020-11-06 | Commencement notice | 1 | 17 | 2023-03-29 | 1 | 1 | 0.13689 | 1.9055 | 2.3901 | 7.1125 | Primary | High |  | CIS | 1816 | SHIP LA Construction | Completed | Q4-2022 | Construction
2560365 | 2560365 | CIS | P-1401743 | €2.4m - Apartment Development | Other County Limerick | Limerick City West | City Centre | 52.6638 | -8.6235 | 16 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-04-25 | 2026-06-16 | Yes | Yes | 2031-06-15 |  |  | 0 | 0 |  | 0 | 0 | 1.1417 |  |  |  | Additional application on site | Low
178013 | 178013 | Register only (Part 8, not in CIS) |  | Part 8: (i) Provision of 16no. residential terraced units (15no. two storey an | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6028 | -8.7149 | 16 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Commenced (building control) | Under construction | 2017-10-16 | 2017-12-13 | No | No |  | 2019-04-12 | Commencement notice | 1 | 16 |  | 1 | 9 | 0.1588 | 1.3279 |  |  | Primary
20622 | 20622 | CIS | P-1112715 | €3.2m - Change of Use to Apartment Development | Other County Limerick | Limerick City West | City Centre | 52.6601 | -8.6316 | 15 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-07-10 | 2020-10-07 | No | No | 2025-10-06 |  |  | 0 | 0 |  | 0 | 0 | 0.24367 |  |  |  | Primary | High
211454 | 211454 | CIS | P-1195465 | €2.1m - Apartment Development | Other County Limerick | Limerick City West | City Centre | 52.6594 | -8.6348 | 14 | 10–24 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2021-10-15 | 2022-09-21 | Yes | No | 2027-09-20 |  |  | 0 | 0 |  | 0 | 0 | 0.93361 |  |  |  | Primary | High
18219 | 18219 | CIS | P-980328 | €2m - Apartment Development | Other County Limerick | Limerick City West | City Centre | 52.6603 | -8.6356 | 14 | 10–24 | Apartments | Standard planning application | Private | Private | Complete | Complete | 2018-03-08 | 2018-09-11 | No | Yes | 2023-09-10 | 2019-05-28 | Commencement notice | 1 | 14 | 2020-09-15 | 1 | 1 | 0.51198 | 0.7091 | 1.3032 | 10.7426 | Primary | High |  | CIS
228023 | 228023 | CIS | SG-032 | €5.45m - Apartment Development, Limerick | Other County Limerick | Limerick City West | City Centre | 52.662 | -8.6238 | 13 | 10–24 | Apartments | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2022-12-20 | 2023-03-20 | No | No |  | 2026-02-09 | CIS start date | 0 | 0 |  | 0 | 0 | 0.24641 | 2.8939 |  |  | Primary | High
21364 | 21364 | CIS | U-1157017 | €2.5m - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6359 | -8.6903 | 12 | 10–24 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2021-03-25 | 2023-06-22 | Yes | Yes | 2028-06-21 | 2024-04-24 | Commencement notice | 2 | 12 |  | 6 | 10 | 2.2423 | 0.84052 |  |  | Primary | High
19689 | 19689 | CIS | SG-004 | €2.2m - 9 Houses | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.5979 | -8.7061 | 9 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2019-07-11 | 2020-02-27 | Yes | No | 2026-09-05 | 2024-03-21 | Commencement notice | 1 | 8 |  | 8 | 2 | 0.63244 | 4.063 |  |  | Additional application on site | Low
21873 | 21873 | CIS | SG-004 | €1.7 - 9 Houses, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.5995 | -8.7073 | 9 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2021-06-21 | 2022-07-14 | Yes | No | 2027-07-13 | 2024-03-18 | Commencement notice | 1 | 5 | 2026-06-12 | 2 | 2 | 1.0623 | 1.6783 | 2.2341 | 4.0285 | Additional application on site | Low |  | CIS
221381 | 221381 | CIS | SG-018 | €2m - 9 Apartments | Other County Limerick | Limerick City West | City Centre | 52.6563 | -8.6257 | 9 | 1–9 | Apartments | Standard planning application | Private | Private | Complete | Complete | 2022-12-21 | 2023-08-29 | Yes | No | 2028-08-28 | 2024-04-15 | Commencement notice | 1 | 9 | 2025-02-19 | 1 | 1 | 0.6872 | 0.62971 | 0.84873 | 10.604 | Additional application on site | Low |  | CIS
2460075 | 2460075 | CIS | P-1329797 | €816k - 8 Apartment | Other County Limerick | Limerick City West | City Centre | 52.6578 | -8.6341 | 8 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2024-01-31 | 2024-07-17 | Yes | No | 2029-07-16 |  |  | 0 | 0 |  | 0 | 0 | 0.45996 |  |  |  | Additional application on site | Low
18168 | 18168 | CIS | P-978022 | €3m - Mixed Use Development | Other County Limerick | Limerick City West | City Centre | 52.6644 | -8.6227 | 8 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2018-02-26 | 2018-07-19 | Yes | No | 2023-07-18 |  |  | 0 | 0 |  | 0 | 0 | 0.39151 |  |  |  | Primary | High
20466 | 20466 | CIS | SG-018 | €1.7m - 8 Apartments | Other County Limerick | Limerick City West | City Centre | 52.6563 | -8.6258 | 8 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-06-05 | 2021-04-20 | Yes | Yes | 2026-04-19 |  |  | 0 | 0 |  | 0 | 0 | 0.87337 |  |  |  | Primary | High
Part 8 - 1264155 | Part 8 - 1264155 | CIS | SG-031 | €590k - Residential Development / Living Georgian Project, 58 O’Connell Street | Other County Limerick | Limerick City West | City Centre | 52.6605 | -8.6299 | 8 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2022-12-22 | 2022-04-08 | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Additional application on site | Low
2460020 | 2460020 | CIS | SG-034 | €200k - Change of Use to 8 Apartments | Other County Limerick | Limerick City West | City Centre | 52.6611 | -8.6273 | 8 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2024-01-12 | 2024-04-04 | No | No | 2029-04-03 | 2025-05-07 | Commencement notice | 1 | 8 |  | 0 | 0 | 0.22724 | 1.0897 |  |  | Additional application on site | Low
2460151 | 2460151 | CIS | P-1333345 | €1.6m - Change of Use to 7 Apartments, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | 52.6599 | -8.6306 | 7 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2024-02-23 | 2024-08-20 | Yes | No | 2029-08-19 | 2026-04-24 | Commencement notice | 1 | 9 |  | 0 | 0 | 0.49008 | 1.6756 |  |  | Additional application on site | Low
21532 | 21532 | CIS | SG-013 | €858k - Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | 52.6349 | -8.672 | 7 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2021-04-23 | 2022-01-13 | Yes | No | 2027-01-12 | 2022-03-30 | Commencement notice | 1 | 7 | 2022-11-02 | 7 | 7 | 0.72553 | 0.20808 | 0.59411 | 11.7823 | Additional application on site | Low |  | CIS
18892 | 18892 | CIS | P-1009370 | €870k - Apartments | Other County Limerick | Limerick City West | Ballinacurra | 52.6533 | -8.6471 | 6 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2018-09-13 | 2019-02-26 | Yes | No | 2024-02-25 | 2019-08-30 | Commencement notice | 1 | 2 |  | 1 | 1 | 0.45448 | 0.5065 |  |  | Primary | High
2461298 | 2461298 | CIS | P-1383405 | €975k - Change of Use to Restaurant/Apartments | Other County Limerick | Limerick City West | City Centre | 52.6636 | -8.6258 | 6 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2024-12-20 | 2025-06-24 | Yes | No | 2030-06-23 | 2026-02-23 | Commencement notice | 1 | 6 |  | 0 | 0 | 0.50924 | 0.66804 |  |  | Primary | High
2560633 | 2560633 | CIS | SG-004 | €2.4m - 6 Houses | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6003 | -8.7066 | 6 | 1–9 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-06-30 | 2026-04-01 | Yes | No | 2031-03-31 |  |  | 0 | 0 |  | 0 | 0 | 0.75291 |  |  |  | Additional application on site | Low
2560595 | 2560595 | CIS | SG-032 | €819k - 6 Apartments | Other County Limerick | Limerick City West | City Centre | 52.6621 | -8.6241 | 6 | 1–9 | Apartments | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2025-06-22 | 2026-02-11 | Yes | No | 2031-02-10 |  |  | 0 | 0 |  | 0 | 0 | 0.64066 |  |  |  | Additional application on site | Low
19444 | 19444 | CIS | SG-003 | €2.2m - Housing Development | Patrickswell | Limerick City West | Outside city neighbourhoods | 52.6003 | -8.7116 | 5 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2019-05-03 | 2019-11-05 | Yes | No | 2024-11-04 | 2024-04-24 | Commencement notice | 2 | 63 |  | 4 | 7 | 0.50924 | 4.4682 |  |  | Additional application on site | Low
19769 | 19769 | CIS | SG-011 | €782k - Apartment Change of Use, Henry Street | Other County Limerick | Limerick City West | City Centre | 52.6582 | -8.634 | 5 | 1–9 | Apartments | Standard planning application | Public – approved housing body | Public | On Site | Under construction | 2019-08-02 | 2019-10-30 | No | No | 2025-10-28 | 2021-03-22 | Commencement notice | 2 | 10 |  | 0 | 0 | 0.24367 | 1.3936 |  |  | Primary | High |  |  | 1934 | CAS AHB Construction | On Site | Q1-2023 | Construction
2460004 | 2460004 | CIS | SG-034 | €755k - Change of Use to 3 Apartments | Other County Limerick | Limerick City West | City Centre | 52.6614 | -8.6282 | 3 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2024-01-02 | 2024-03-27 | No | No | 2029-03-26 | 2024-12-30 | Commencement notice | 2 | 6 |  | 0 | 0 | 0.23272 | 0.76112 |  |  | Primary | High
19841 | 19841 | CIS | P-1064271 | €618k - 2 Apartments | Other County Limerick | Limerick City West | City Centre | 52.656 | -8.6284 | 2 | 1–9 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2019-08-27 | 2020-09-16 | Yes | No | 2025-09-15 | 2023-09-05 | Commencement notice | 1 | 4 |  | 0 | 0 | 1.0568 | 2.9678 |  |  | Primary | High
187001 | 187001 | CIS | SG-001 | €18.9m - Housing Development | Mungret | Limerick City West | Dooradoyle | 52.6381 | -8.6767 | 0 | Unknown | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2018-01-09 | 2018-04-10 | Yes | No | 2029-03-12 |  |  | 0 | 0 |  | 0 | 0 | 0.24914 |  |  |  | Extension of duration (parent not in CIS) | Low
19990 | 19990 | CIS | SG-013 | €521k - 8 Houses | Mungret | Limerick City West | Dooradoyle | 52.6343 | -8.6714 | 0 | Unknown | Houses | Standard planning application | Private | Private | Complete | Complete | 2019-10-04 | 2020-01-10 | No | No | 2023-02-26 | 2020-12-04 | Commencement notice | 1 | 8 | 2021-06-02 | 1 | 8 | 0.26831 | 0.90075 | 0.49281 | 0 | Primary | High |  | CIS
201142 | 201142 | CIS | P-1132789 | €919k - Student Accommodation Development, Saint Gerard Street | Other County Limerick | Limerick City West | City Centre | 52.6568 | -8.6344 |  | Unknown | Student | Standard planning application | Private | Private | Permission Granted | Not started – past expiry | 2020-11-09 | 2021-09-21 | Yes | No | 2026-09-20 |  |  | 0 | 0 |  | 0 | 0 | 0.86516 |  |  |  | Primary | High
22840 | 22840 | CIS | P-1243349 | €21m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4573 | -9.0629 | 93 | 50–99 | Mixed | Standard planning application | Private | Private | Part Complete | Under construction | 2022-07-29 | 2023-06-26 | Yes | No | 2028-06-25 | 2024-01-31 | Commencement notice | 7 | 79 |  | 1 | 1 | 0.90897 | 0.59959 |  |  | Primary | High
21594 | 21594 | CIS | U-1165485 | €11.3m - Residential Development | Abbeyfeale | Newcastle West | Outside city neighbourhoods | 52.382 | -9.2983 | 68 | 50–99 | Apartments | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2021-05-05 | 2022-09-06 | Yes | Yes | 2027-09-05 |  |  | 0 | 0 |  | 0 | 0 | 1.3388 |  |  |  | Primary | High | On hold / no movement
21531 | 21531 | CIS | SG-022 | €9.7m - Housing Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4426 | -9.052 | 61 | 50–99 | Apartments | Standard planning application | Private | Private | Commencement Expected | Under construction | 2021-04-23 | 2022-05-03 | Yes | No | 2027-05-02 | 2022-09-16 | Commencement notice | 4 | 51 |  | 6 | 15 | 1.0267 | 0.37235 |  |  | Primary | High
2360706 | 2360706 | CIS | P-1310783 | €8.9m - Housing Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4543 | -9.0666 | 53 | 50–99 | Houses | Standard planning application | Private | Private | Stalled or Suspended | Not started – permission live | 2023-09-25 | 2024-07-09 | Yes | No | 2029-07-08 |  |  | 0 | 0 |  | 0 | 0 | 0.7885 |  |  |  | Primary | High | On hold / no movement
2660232 | 2660232 | CIS | U-1446285 | €7.8m - Residential Development, Abbeyfeale | Abbeyfeale | Newcastle West | Outside city neighbourhoods | 52.3821 | -9.2984 | 48 | 25–49 | Apartments | Standard planning application | Private | Private | Plans Submitted | In planning | 2026-03-03 |  | Yes | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Additional application on site | Low
228020 | 228020 | CIS | P-1258895 | €4.9m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4585 | -9.0506 | 31 | 25–49 | Unknown | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2022-11-14 | 2023-02-10 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.24093 |  |  |  | Primary | High
2660575 | 2660575 | CIS | U-1360912 | €4.3m - Apartment Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4535 | -9.0541 | 30 | 25–49 | Apartments | Standard planning application | Private | Private | Plans Submitted | In planning | 2026-05-22 |  | Yes | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
2460568 | 2460568 | CIS | P-1350850 | €3.9m - Residential Development, Castlemahon | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.4311 | -9.0109 | 18 | 10–24 | Apartments | Standard planning application | Private | Private | Commencement Expected | Under construction | 2024-06-07 | 2025-03-07 | Yes | No | 2030-03-06 | 2025-10-09 | Commencement notice | 2 | 16 |  | 0 | 0 | 0.74743 | 0.59138 |  |  | Primary | High
218012 | 218012 | CIS | SG-023 | €2.4m - Residential Development | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.3446 | -8.9739 | 18 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | Part Complete | Under construction | 2021-12-06 | 2022-02-25 | No | No |  | 2025-06-26 | Commencement notice | 1 | 11 |  | 1 | 11 | 0.22177 | 3.332 |  |  | Additional application on site | Low
2360826 | 2360826 | CIS | P-1318536 | €2.2m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.46 | -9.0642 | 14 | 10–24 | Houses | Standard planning application | Private | Private | Permission Granted | Not started – permission live | 2023-11-14 | 2024-05-15 | Yes | No | 2029-05-14 |  |  | 0 | 0 |  | 0 | 0 | 0.50103 |  |  |  | Primary | High
2460082 | 2460082 | CIS | SG-022 | €1.9m - Apartment Development | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4426 | -9.0528 | 12 | 10–24 | Apartments | Standard planning application | Private | Private | On Site | Under construction | 2024-02-02 | 2024-05-01 | No | No | 2027-05-02 | 2024-09-30 | Commencement notice | 1 | 12 |  | 0 | 0 | 0.24367 | 0.41615 |  |  | Additional application on site | Low
258297 | 258297 | CIS | U-1414882 | €4.5m - Residential Development, Abbeyfeale | Abbeyfeale | Newcastle West | Outside city neighbourhoods | 52.383 | -9.2836 | 12 | 10–24 | Houses | Part 8 / council | Public – approved housing body | Public | Tender | Not started – permission live | 2025-10-06 |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1694 | CALF Construction | Stage 4 Tender Report / Final Turnkey or CALF Approval | Q3-2025 | Construction
228013 | 228013 | CIS | P-1237333 | €2.2m - Housing Development, Ardagh | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.496 | -9.0634 | 10 | 10–24 | Unknown | Part 8 / council | Public – local authority | Public | On Site | Under construction | 2022-06-24 | 2022-08-29 | No | No |  | 2025-10-13 | Commencement notice | 3 | 10 |  | 0 | 0 | 0.1807 | 3.1239 |  |  | Primary | High |  |  | 1827 | SHIP LA Construction | On Site | Q1-2023 | Construction
2460028 | 2460028 | CIS | U-1327665 | €2.5m - Assisted Living Dwelling Units, Glin | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.5698 | -9.2806 | 10 | 10–24 | Houses | Standard planning application | Public – approved housing body | Public | Tender | Not started – permission live | 2024-01-17 | 2024-09-02 | Yes | No | 2029-09-01 |  |  | 0 | 0 |  | 0 | 0 | 0.62697 |  |  |  | Primary | High |  |  | 1939 | CAS AHB Construction | Stage 3 Pre-Tender Design | Q4-2025 | Construction
2561211 | 2561211 | CIS | U-1417331 | €1.8m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4526 | -9.0584 | 10 | 10–24 | Apartments | Standard planning application | Private | Private | Contract Awarded | Not started – permission live | 2025-11-21 | 2026-02-26 | No | No | 2031-02-25 |  |  | 0 | 0 |  | 0 | 0 | 0.26557 |  |  |  | Primary | High
2660063 | 2660063 | CIS | U-1422361 | €1.8m - 7 House/Apartment/Community Office, Feenagh | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.3901 | -8.8796 | 8 | 1–9 | Mixed | Standard planning application | Public – approved housing body | Public | Plans Submitted | In planning | 2026-01-26 |  | Yes | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High |  |  | 1940 | CAS AHB Construction | Stage 2 Pre-Planning | Q3-2024 | Construction
188013 | 188013 | CIS | P-1007351 | €701k - 7 Houses | Abbeyfeale | Newcastle West | Outside city neighbourhoods | 52.3868 | -9.3011 | 7 | 1–9 | Houses | Part 8 / council | Public – local authority | Public | Permission Granted | Not started – permission live | 2018-08-27 | 2018-09-25 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.079398 |  |  |  | Primary | High
2460046 | 2460046 | CIS | U-1328561 | €2m - 7 Houses, Broadford | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.3459 | -8.9745 | 7 | 1–9 | Houses | Standard planning application | Public – approved housing body | Public | Tender | Not started – permission live | 2024-01-24 | 2024-08-16 | Yes | No | 2029-08-15 |  |  | 0 | 0 |  | 0 | 0 | 0.56126 |  |  |  | Additional application on site | Low
18994 | 18994 | CIS | P-1014706 | €553k - 6 Houses | Newcastle West | Newcastle West | Outside city neighbourhoods | 52.4566 | -9.048 | 6 | 1–9 | Houses | Standard planning application | Private | Private | Complete | Complete | 2018-10-12 | 2019-11-13 | Yes | No | 2024-11-12 | 2023-07-12 | Commencement notice | 1 | 6 | 2026-05-28 | 2 | 6 | 1.0869 | 3.6605 | 2.8775 | 2.0852 | Primary | High |  | CIS
20678 | 20678 | CIS | P-1114096 | €864k - Residential Development, Tournafulla | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.367 | -9.1462 | 4 | 1–9 | Houses | Standard planning application | Private | Private | On Site | Under construction | 2020-07-17 | 2021-07-22 | Yes | No | 2026-07-21 | 2021-11-06 | Commencement notice | 1 | 1 |  | 0 | 0 | 1.013 | 0.29295 |  |  | Primary | High
Part 8 - 1316160 | Part 8 - 1316160 | CIS | U-1316160 | €705k - Radharc an Ghleanna Residential Development, Mountcollins | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.3187 | -9.2333 | 4 | 1–9 | Unknown | Part 8 / council | Public – local authority | Public | Tender | Not started – permission live | 2023-10-27 | 2024-02-13 | No | No |  |  |  | 0 | 0 |  | 0 | 0 | 0.29843 |  |  |  | Primary | High
20857 | 20857 | CIS | P-1121263 | €543k - 2 Houses | Other County Limerick | Newcastle West | Outside city neighbourhoods | 52.456 | -9.2837 | 2 | 1–9 | Houses | Standard planning application | Private | Private | Commencement Expected | Under construction | 2020-09-01 | 2020-11-25 | No | No | 2025-11-24 | 2022-11-04 | Commencement notice | 4 | 4 |  | 0 | 0 | 0.23272 | 1.9411 |  |  | Primary | High
|  | CIS | U-1424651 | €20m - Council Housing Programme 2026 - 2030, Limerick | Limerick City and Suburbs | Unknown | Unknown |  |  | 0 | Unknown | Unknown | Standard planning application | Public – local authority | Public | Tender | Not started – permission live |  |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High
|  | CIS | U-1438055 | €1.5m - Multi-Party Framework for Maintenance Repairs and Replacement of Heating Systems, Limerick | Limerick City and Suburbs | Unknown | Unknown |  |  |  | Unknown | Unknown | Standard planning application | Public – local authority | Public | Tender | Not started – permission live |  |  | No | No |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Primary | High

## Status (live)
Units with permission by status and size band
Size band | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units
1–9 | 69 | 110 | 154 | 93 | 24 | 381
10–24 | 69 | 230 | 382 | 396 | 101 | 1109
25–49 | 47 | 221 | 562 | 745 | 49 | 1577
50–99 | 36 | 276 | 1456 | 952 | 0 | 2684
100+ | 23 | 438 | 1510 | 2957 | 137 | 5042
All | 244 | 1275 | 4064 | 5143 | 311 | 10793
Units with permission by status and LEA
LEA | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units
Limerick City East | 56 | 797 | 943 | 2089 | 149 | 3978
Limerick City North | 48 | 170 | 717 | 793 | 16 | 1696
Limerick City West | 77 | 182 | 1962 | 1559 | 121 | 3824
Adare-Rathkeale | 19 | 16 | 66 | 335 | 3 | 420
Cappamore-Kilmallock | 30 | 104 | 158 | 151 | 22 | 435
Newcastle West | 19 | 6 | 218 | 216 | 0 | 440
Units with permission by status and city neighbourhood
Neighbourhood | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units
City Centre | 40 | 83 | 127 | 715 | 55 | 980
Kings Island | 2 | 0 | 0 | 50 | 0 | 50
Corbally/Grove Island | 4 | 24 | 26 | 40 | 0 | 90
Singland/Garryowen | 16 | 22 | 146 | 132 | 4 | 304
Castletroy/Annacotty | 32 | 474 | 746 | 1590 | 149 | 2959
Southhill | 12 | 284 | 21 | 418 | 0 | 723
Dooradoyle | 22 | 98 | 1133 | 689 | 0 | 1920
Ballinacurra | 4 | 17 | 398 | 0 | 0 | 415
Caherdavin | 24 | 125 | 566 | 607 | 12 | 1310
Outside city neighbourhoods | 93 | 148 | 901 | 902 | 91 | 2042
Units with permission by status and sector
Sector | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units
Public | 65 | 301 | 717 | 518 | 33 | 1569
Private | 186 | 974 | 3347 | 4625 | 278 | 9224

## 1 Status by size
Size band (units) | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units
1–9 | 69 | 110 | 154 | 93 | 24 | 381
10–24 | 69 | 230 | 382 | 396 | 101 | 1109
25–49 | 47 | 221 | 562 | 745 | 49 | 1577
50–99 | 36 | 276 | 1456 | 952 | 0 | 2684
100+ | 23 | 438 | 1510 | 2957 | 137 | 5042
All | 244 | 1275 | 4064 | 5143 | 311 | 10793
Values calculated in delivery_analysis.py from the Schemes sheet.

## 2 Timeline by size
Size band (units) | Approval: n | Approval: LQ | Approval: median | Approval: UQ | Grant to start: n | Grant to start: LQ | Grant to start: median | Grant to start: UQ | Start to completion: n | Start to completion: median | Build rate (dpa): median
1–9 | 65 | 0.2 | 0.5 | 0.8 | 45 | 0.7 | 1.3 | 2.1 | 18 | 1.7 | 4.1
10–24 | 65 | 0.3 | 0.6 | 0.9 | 34 | 0.6 | 1.4 | 2 | 15 | 1.8 | 8.3
25–49 | 47 | 0.3 | 0.6 | 0.9 | 23 | 0.8 | 1.6 | 2.1 | 6 | 1.4 | 21.5
50–99 | 36 | 0.6 | 0.7 | 1.2 | 23 | 0.7 | 1.1 | 2.1 | 4 | 2.3 | 34
100+ | 23 | 0.3 | 0.5 | 0.7 | 10 | 1.1 | 1.7 | 1.9 | 3 | 2.1 | 50.3
All | 240 | 0.3 | 0.6 | 0.9 | 136 | 0.7 | 1.3 | 2.1 | 47 | 1.8 | 8
Values calculated in delivery_analysis.py from the Schemes sheet.

## 3 Share started over time
Scheme size | Started within 1 yr (%) | n (1 yr) | Started within 2 yr (%) | n (2 yr) | Started within 3 yr (%) | n (3 yr) | Started within 4 yr (%) | n (4 yr) | Started within 5 yr (%) | n (5 yr)
1–24 units | 27 | 119 | 47 | 106 | 54 | 82 | 64 | 70 | 68 | 50
25–99 units | 22 | 72 | 47 | 60 | 65 | 48 | 71 | 38 | 84 | 31
100+ units | 14 | 14 | 67 | 12 | 67 | 9 | 62 | 8 |  | 4
All | 25 | 208 | 48 | 181 | 58 | 142 | 66 | 119 | 72 | 88
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4a Implementation by LEA
lea | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Limerick City East | 39 | 1834 | 1673 | 36 | 91 | 92 | 1.2
Limerick City North | 34 | 1362 | 838 | 20 | 62 | 59 | 1.4
Limerick City West | 58 | 2487 | 2084 | 38 | 84 | 66 | 1.4
Adare-Rathkeale | 11 | 179 | 31 | 4 | 17 | 36 | 2.1
Cappamore-Kilmallock | 23 | 323 | 192 | 18 | 59 | 78 | 1.8
Newcastle West | 16 | 400 | 206 | 8 | 52 | 50 | 1.3
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4b Implementation by size
band | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
1–9 | 55 | 297 | 216 | 40 | 73 | 73 | 1.4
10–24 | 51 | 836 | 530 | 32 | 63 | 63 | 1.5
25–49 | 32 | 1093 | 652 | 19 | 60 | 59 | 1.8
50–99 | 28 | 2109 | 1678 | 22 | 80 | 79 | 1.2
100+ | 12 | 2250 | 1948 | 10 | 87 | 83 | 1.7
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4c Implementation by type
dwelling_type | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Houses | 75 | 1381 | 954 | 54 | 69 | 72 | 1.3
Mixed | 28 | 3260 | 2773 | 24 | 85 | 86 | 1.7
Apartments | 52 | 1452 | 978 | 30 | 67 | 58 | 1.7
Student | 4 | 82 | 26 | 1 | 32 | 25 | 1.6
Unknown | 22 | 410 | 293 | 15 | 71 | 68 | 1.8
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4d Implementation by route
route | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Standard planning application | 138 | 4178 | 3071 | 93 | 74 | 67 | 1.3
LRD | 3 | 315 | 315 | 3 | 100 | 100 | 1
SHD (An Bord Pleanála) | 5 | 1257 | 955 | 3 | 76 | 60 | 1.8
Part 8 / council | 35 | 835 | 683 | 25 | 82 | 71 | 1.8
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4e Implementation by settlement
settlement | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Other County Limerick | 87 | 2526 | 1649 | 51 | 65 | 59 | 1.6
Limerick City and Suburbs | 40 | 1958 | 1838 | 33 | 94 | 82 | 1.4
Mungret | 13 | 802 | 781 | 11 | 97 | 85 | 0.8
Patrickswell | 13 | 396 | 282 | 10 | 71 | 77 | 3.6
Newcastle West | 7 | 270 | 172 | 4 | 64 | 57 | 0.5
Annacotty | 2 | 149 | 12 | 1 | 8 | 50 | 0.6
Castleconnell | 3 | 129 | 129 | 3 | 100 | 100 | 1.1
Kilmallock | 5 | 92 | 92 | 5 | 100 | 100 | 2.1
Abbeyfeale | 2 | 75 | 0 | 0 | 0 | 0
Bruff | 1 | 74 | 0 | 0 | 0 | 0
Cappamore | 3 | 49 | 49 | 3 | 100 | 100 | 1.7
Rathkeale | 1 | 31 | 0 | 0 | 0 | 0
Croom | 1 | 14 | 0 | 0 | 0 | 0
Adare | 2 | 11 | 11 | 2 | 100 | 100 | 2.3
Caherconlish | 1 | 9 | 9 | 1 | 100 | 100 | 2.1
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4f Implementation by owner
owner | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Public – local authority | 36 | 838 | 686 | 26 | 82 | 72 | 1.7
Public – approved housing body | 14 | 319 | 265 | 9 | 83 | 64 | 2
Private | 131 | 5428 | 4073 | 89 | 75 | 68 | 1.2
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4g Implementation by sector
sector | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
Public | 50 | 1157 | 951 | 35 | 82 | 70 | 1.8
Private | 131 | 5428 | 4073 | 89 | 75 | 68 | 1.2
Values calculated in delivery_analysis.py from the Schemes sheet.

## 4h Implementation by nbhd
nbhd | Schemes | Units permitted | Units started | Schemes started | Units started (%) | Schemes started (%) | Median grant to start (yrs)
City Centre | 28 | 409 | 184 | 14 | 45 | 50 | 1.6
Kings Island | 1 | 27 | 0 | 0 | 0 | 0
Corbally/Grove Island | 2 | 50 | 50 | 2 | 100 | 100 | 0.6
Singland/Garryowen | 9 | 149 | 123 | 6 | 83 | 67 | 1.7
Castletroy/Annacotty | 24 | 1363 | 1214 | 22 | 89 | 92 | 1.5
Southhill | 7 | 288 | 288 | 7 | 100 | 100 | 1.6
Dooradoyle | 16 | 1282 | 1231 | 13 | 96 | 81 | 0.8
Ballinacurra | 4 | 415 | 415 | 4 | 100 | 100 | 1.2
Caherdavin | 20 | 1130 | 663 | 11 | 59 | 55 | 1.1
Outside city neighbourhoods | 70 | 1472 | 856 | 45 | 58 | 64 | 1.8
Values calculated in delivery_analysis.py from the Schemes sheet.

## 12 Status by nbhd
Neighbourhood | Schemes | Complete | Under construction | Not started – permission live | Not started – past expiry | Total units | Public units | Public share (%)
City Centre | 40 | 83 | 127 | 715 | 55 | 980 | 392 | 40
Kings Island | 2 | 0 | 0 | 50 | 0 | 50 | 50 | 100
Corbally/Grove Island | 4 | 24 | 26 | 40 | 0 | 90 | 0 | 0
Singland/Garryowen | 16 | 22 | 146 | 132 | 4 | 304 | 59 | 19
Castletroy/Annacotty | 32 | 474 | 746 | 1590 | 149 | 2959 | 6 | 0
Southhill | 12 | 284 | 21 | 418 | 0 | 723 | 104 | 14
Dooradoyle | 22 | 98 | 1133 | 689 | 0 | 1920 | 270 | 14
Ballinacurra | 4 | 17 | 398 | 0 | 0 | 415 | 38 | 9
Caherdavin | 24 | 125 | 566 | 607 | 12 | 1310 | 251 | 19
Outside city neighbourhoods | 93 | 148 | 901 | 902 | 91 | 2042 | 399 | 20
Values calculated in delivery_analysis.py from the Schemes sheet.

## 2b Timeline by sector
Sector | Schemes | Units | Approval: median | Grant to start: median | Grant to start: n | Start to completion: median | Start to completion: n | Build rate (dpa): median
Public | 76 | 1737 | 0.3 | 1.7 | 36 | 1.5 | 18 | 7.6
Private | 189 | 9306 | 0.7 | 1 | 100 | 1.8 | 29 | 10.6
Values calculated in delivery_analysis.py from the Schemes sheet.

## 3b Started over time by sector
Sector | Started within 1 yr (%) | n (1 yr) | Started within 2 yr (%) | n (2 yr) | Started within 3 yr (%) | n (3 yr) | Started within 4 yr (%) | n (4 yr) | Started within 5 yr (%) | n (5 yr)
Public | 8 | 53 | 44 | 50 | 58 | 43 | 69 | 35 | 60 | 25
Private | 30 | 155 | 50 | 131 | 58 | 99 | 64 | 84 | 76 | 63
Values calculated in delivery_analysis.py from the Schemes sheet.

## 5 Planning path
Planning path | Schemes | Median approval (yrs) | LQ | UQ | Units
No further information, no appeal | 31 | 0.2 | 0.2 | 0.2 | 1441
Further information requested | 126 | 0.7 | 0.5 | 0.8 | 4543
Appealed | 48 | 1.3 | 0.9 | 1.7 | 2703
Values calculated in delivery_analysis.py from the Schemes sheet.

## 6 Expiry of unstarted
Expiry window | Schemes | Adare-Rathkeale | Cappamore-Kilmallock | Limerick City East | Limerick City North | Limerick City West | Newcastle West | Total units
Already past expiry | 14 | 3 | 22 | 149 | 16 | 121 | 0 | 311
Within 12 months | 8 | 65 | 0 | 0 | 190 | 51 | 68 | 374
12–24 months | 6 | 32 | 0 | 0 | 90 | 83 | 0 | 205
24–36 months | 20 | 17 | 113 | 0 | 196 | 116 | 84 | 526
More than 36 months | 43 | 190 | 35 | 2072 | 262 | 1257 | 10 | 3826
No expiry date (mainly Part 8) | 17 | 31 | 3 | 17 | 55 | 52 | 54 | 212
Values calculated in delivery_analysis.py from the Schemes sheet.

## 7 Expiry watchlist
Planning ref | Site ID | Scheme | Settlement | LEA | Neighbourhood | Owner | Units | Size band | Type | Permission granted | Expiry | Expiry window | CIS stage | Last CIS update | CIS notes
18168 | P-978022 | €3m - Mixed Use Development | Other County Limerick | Limerick City West | City Centre | Private | 8 | 1–9 | Apartments | 2018-07-19 | 2023-07-18 | Already past expiry | Permission Granted | 2018-06-20 15:14
18346 | SG-004 | €6.3m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | Private | 49 | 25–49 | Houses | 2018-10-23 | 2023-10-22 | Already past expiry | Permission Granted | 2023-09-18 14:40 | Permission expiring
19302 | U-1040199 | €2.6m - Apartments | Limerick City and Suburbs | Limerick City North | Caherdavin | Public – approved housing body | 12 | 10–24 | Apartments | 2019-06-19 | 2024-06-18 | Already past expiry | Tender | 2019-09-30 09:48
19149 | U-1034286 | €567k - Change of Use to Care Residential Units | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | Public – approved housing body | 21 | 10–24 | Apartments | 2019-09-11 | 2024-09-10 | Already past expiry | Tender | 2023-11-21 09:30
| P-1015929 | €2m - Housing Development | Other County Limerick | Limerick City West | Outside city neighbourhoods | Private | 17 | 10–24 | Unknown | 2019-09-27 | 2024-09-27 | Already past expiry | Permission Granted | 2018-10-30 12:04
197025 | SG-014 | Housing Development | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 12 | 10–24 | Houses | 2020-02-07 | 2024-12-01 | Already past expiry | Permission Granted | 2020-03-24 08:13
20341 | P-1099323 | €574k - Extension to Pub | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 1 | 1–9 | Unknown | 2020-09-24 | 2025-09-23 | Already past expiry | Permission Granted | 2020-08-21 13:34
20622 | P-1112715 | €3.2m - Change of Use to Apartment Development | Other County Limerick | Limerick City West | City Centre | Private | 15 | 10–24 | Apartments | 2020-10-07 | 2025-10-06 | Already past expiry | Permission Granted | 2020-09-07 08:09
20222 | SG-017 | €8.9m - Mixed Use Development, 34-41 Catherine Street | Other County Limerick | Limerick City West | City Centre | Private | 24 | 10–24 | Apartments | 2021-01-06 | 2026-01-05 | Already past expiry | Permission Granted | 2020-12-01 11:38
20466 | SG-018 | €1.7m - 8 Apartments | Other County Limerick | Limerick City West | City Centre | Private | 8 | 1–9 | Apartments | 2021-04-20 | 2026-04-19 | Already past expiry | Permission Granted | 2021-04-29 14:19
ABPREF309999 | P-1163033 | €30m - Residential Development, Annacotty | Annacotty | Limerick City East | Castletroy/Annacotty | Private | 137 | 100+ | Mixed | 2021-08-05 | 2026-08-04 | Already past expiry | Permission Granted | 2023-10-27 11:38 | On hold / no movement
20827 | P-1120093 | €864k - 4 Houses | Other County Limerick | Limerick City North | Singland/Garryowen | Private | 4 | 1–9 | Houses | 2021-08-26 | 2026-08-25 | Already past expiry | Permission Granted | 2021-07-27 11:09
2360207 | P-1283723 | €680k - 3 Houses | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | Private | 3 | 1–9 | Houses | 2023-09-18 | 2026-09-17 | Already past expiry | Permission Granted | 2023-08-17 11:04
201142 | P-1132789 | €919k - Student Accommodation Development, Saint Gerard Street | Other County Limerick | Limerick City West | City Centre | Private |  | Unknown | Student | 2021-09-21 | 2026-09-20 | Already past expiry | Permission Granted | 2021-08-20 11:30
20525 |  | Register: the construction of 14 dwelling houses, including 2 no semi-detached 2 | Croom | Adare-Rathkeale | Outside city neighbourhoods | Private | 14 | 10–24 | Houses | 2021-12-02 | 2026-12-01 | Within 12 months | Permission Granted
21147 | SG-021 | €1.4m - Housing Development | Limerick City and Suburbs | Limerick City North | Caherdavin | Private | 11 | 10–24 | Apartments | 2022-02-07 | 2027-02-06 | Within 12 months | Permission Granted | 2022-01-04 07:22
21835 | SG-025 | €3.5m - Apartment Development, Limerick | Other County Limerick | Limerick City North | Singland/Garryowen | Private | 14 | 10–24 | Apartments | 2022-02-17 | 2027-02-16 | Within 12 months | Permission Granted | 2022-01-13 15:34
21630 | U-1166991 | €10.8m - Residential Development, Croom | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | Private | 51 | 50–99 | Houses | 2022-05-12 | 2027-05-11 | Within 12 months | Contract Awarded | 2024-06-18 14:05
211598 | SG-026 | €5.8m - Apartment/Retail Development, Limerick | Other County Limerick | Limerick City West | City Centre | Private | 37 | 25–49 | Apartments | 2022-05-25 | 2027-05-24 | Within 12 months | Permission Granted | 2022-04-21 12:09
ABPREF312683 | P-1214059 | €27.5m - Clonmacken Gardens Housing Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | Private | 165 | 100+ | Mixed | 2022-05-26 | 2027-05-25 | Within 12 months | Permission Granted | 2026-02-25 08:37
21594 | U-1165485 | €11.3m - Residential Development | Abbeyfeale | Newcastle West | Outside city neighbourhoods | Private | 68 | 50–99 | Apartments | 2022-09-06 | 2027-09-05 | Within 12 months | Contract Awarded | 2023-10-18 11:29 | On hold / no movement
211454 | P-1195465 | €2.1m - Apartment Development | Other County Limerick | Limerick City West | City Centre | Private | 14 | 10–24 | Apartments | 2022-09-21 | 2027-09-20 | Within 12 months | Permission Granted | 2022-08-24 14:33
22410 | P-1225380 | €18.8m - Nursing Home Development, Croom | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | Private | 32 | 25–49 | Unknown | 2023-02-20 | 2028-02-19 | 12–24 months | Permission Granted | 2023-01-19 11:45
221107 | U-1254537 | €5m - Apartment/Retail Development, Dooradoyle | Limerick City and Suburbs | Limerick City West | Dooradoyle | Private | 30 | 25–49 | Apartments | 2023-06-14 | 2028-06-13 | 12–24 months | Permission Granted | 2023-05-16
22817 | P-1242233 | €11m - Residential Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | Private | 86 | 50–99 | Mixed | 2023-07-04 | 2028-07-03 | 12–24 months | Permission Granted | 2023-06-01 10:58
221003 | U-1250272 | €6.5m - Apartment Development, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | Private | 29 | 25–49 | Apartments | 2023-07-12 | 2028-07-11 | 12–24 months | Permission Granted | 2023-06-13
23283 | P-1292276 | €907k - Change of Use to 4 Apartments | Other County Limerick | Limerick City North | City Centre | Public – approved housing body | 4 | 1–9 | Apartments | 2023-08-16 | 2028-08-15 | 12–24 months | Permission Granted | 2023-07-18 10:52
221367 | SG-031 | €5.2m - Residential Development, Limerick | Other County Limerick | Limerick City West | City Centre | Private | 24 | 10–24 | Apartments | 2023-09-13 | 2028-09-12 | 12–24 months | Permission Granted | 2023-08-15 09:57 | Site for sale / sold
22917 | SG-027 | €3.6m - Mixed Use Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | Private | 12 | 10–24 | Houses | 2023-10-03 | 2028-10-02 | 24–36 months | Permission Granted | 2023-08-31 10:50
2461101 | SG-030 | €1.4m - 7 Houses | Cappamore | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 7 | 1–9 | Houses | 2025-07-30 | 2028-10-16 | 24–36 months | Permission Granted | 2025-07-07 08:46
19552 | P-1051821 | €2m - Apartment Development | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | Private | 14 | 10–24 | Apartments | 2020-11-13 | 2028-11-13 | 24–36 months | Permission Granted | 2020-11-18 10:40
2360144 | U-1277663 | €9m - Housing Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | Private | 41 | 25–49 | Houses | 2023-11-15 | 2028-11-14 | 24–36 months | Contract Awarded | 2025-06-23 08:58
191298 | P-1084266 | €5.6m - Housing Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 32 | 25–49 | Houses | 2020-11-26 | 2028-11-25 | 24–36 months | Stalled or Suspended | 2023-10-13 14:41 | On hold / no movement
22471 | U-1227182 | €4.5m - Housing Development, Mungret | Mungret | Limerick City West | Dooradoyle | Private | 21 | 10–24 | Houses | 2024-01-22 | 2029-01-21 | 24–36 months | Permission Granted | 2024-01-25
187001 | SG-001 | €18.9m - Housing Development | Mungret | Limerick City West | Dooradoyle | Private | 0 | Unknown | Houses | 2018-04-10 | 2029-03-12 | 24–36 months | Permission Granted | 2018-04-11 16:38
19710 | P-1058796 | €8.5m - Student Accommodation Development, Former Hassett’s Bar | Other County Limerick | Limerick City North | Caherdavin | Private | 31 | 25–49 | Student | 2021-03-15 | 2029-03-13 | 24–36 months | Stalled or Suspended | 2022-08-26 09:53 | On hold / no movement
211800 | SG-027 | €21m - Residential Development, Old Cratloe Road | Other County Limerick | Limerick City North | Caherdavin | Private | 99 | 50–99 | Mixed | 2024-04-08 | 2029-04-07 | 24–36 months | Permission Granted | 2024-05-13 05:22
2360794 | P-1316492 | €15.3m - Residential Development, Bruff | Bruff | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 74 | 50–99 | Houses | 2024-05-07 | 2029-05-06 | 24–36 months | Permission Granted | 2024-08-28 09:05 | Site for sale / sold
2360826 | P-1318536 | €2.2m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | Private | 14 | 10–24 | Houses | 2024-05-15 | 2029-05-14 | 24–36 months | Permission Granted | 2024-04-16 09:48
221172 | P-1256924 | €5.9m - Student Accommodation Development | Other County Limerick | Limerick City West | City Centre | Private | 25 | 25–49 | Student | 2024-05-30 | 2029-05-29 | 24–36 months | Permission Granted | 2024-06-07 07:08
2460299 | P-1339954 | €884k - 3 Houses | Other County Limerick | Adare-Rathkeale | Outside city neighbourhoods | Private | 3 | 1–9 | Houses | 2024-07-02 | 2029-07-01 | 24–36 months | Permission Granted | 2024-05-31 09:28
2360706 | P-1310783 | €8.9m - Housing Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | Private | 53 | 50–99 | Houses | 2024-07-09 | 2029-07-08 | 24–36 months | Stalled or Suspended | 2024-09-19 11:50 | On hold / no movement
2360345 | P-1290708 | €3.7m - Residential Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | Private | 21 | 10–24 | Apartments | 2024-07-09 | 2029-07-08 | 24–36 months | Permission Granted | 2023-08-24 10:25
2460075 | P-1329797 | €816k - 8 Apartment | Other County Limerick | Limerick City West | City Centre | Private | 8 | 1–9 | Apartments | 2024-07-17 | 2029-07-16 | 24–36 months | Permission Granted | 2024-06-18 10:37
2360759 | SG-025 | €1.4m - Retail Units/Apartments | Other County Limerick | Limerick City North | Singland/Garryowen | Private | 8 | 1–9 | Apartments | 2024-07-17 | 2029-07-16 | 24–36 months | Permission Granted | 2024-06-18 10:38
221400 | P-1265188 | €10.4m - Residential Development, Thomondgate | Other County Limerick | Limerick City North | Caherdavin | Private | 46 | 25–49 | Apartments | 2024-07-26 | 2029-07-25 | 24–36 months | Permission Granted | 2024-08-01 09:29
2460046 | U-1328561 | €2m - 7 Houses, Broadford | Other County Limerick | Newcastle West | Outside city neighbourhoods | Public – approved housing body | 7 | 1–9 | Houses | 2024-08-16 | 2029-08-15 | 24–36 months | Tender | 2026-03-30 07:44
2460028 | U-1327665 | €2.5m - Assisted Living Dwelling Units, Glin | Other County Limerick | Newcastle West | Outside city neighbourhoods | Public – approved housing body | 10 | 10–24 | Houses | 2024-09-02 | 2029-09-01 | 24–36 months | Tender | 2026-04-24 11:37
221114 | SG-027 | €12.2m - Residential Development, Limerick | Other County Limerick | Limerick City North | Caherdavin | Private | 54 | 50–99 | Houses | 2024-10-18 | 2029-10-17 | More than 36 months | Permission Granted | 2024-10-24 09:38
22959 | SG-027 | €20m - Residential Development, Limerick. | Other County Limerick | Limerick City North | Caherdavin | Private | 98 | 50–99 | Houses | 2024-11-21 | 2029-11-20 | More than 36 months | Permission Granted | 2024-11-28 10:22
24151 |  | Register: the construction of 10 dwelling units to include 2 no. detached 5 bedr | Croom | Adare-Rathkeale | Outside city neighbourhoods | Private | 10 | 10–24 | Houses | 2025-01-15 | 2030-01-14 | More than 36 months | Permission Granted
2460570 | P-1350852 | €4.5m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | Private | 40 | 25–49 | Apartments | 2025-02-06 | 2030-02-05 | More than 36 months | Permission Granted | 2025-02-07 11:16
22990 | SG-015 | €22m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | Private | 99 | 50–99 | Mixed | 2025-02-25 | 2030-02-24 | More than 36 months | Permission Granted | 2025-03-07 14:55
2460030 | SG-010 | €2.9m - Residential Development | Castleconnell | Limerick City East | Outside city neighbourhoods | Private | 14 | 10–24 | Houses | 2025-03-12 | 2030-03-11 | More than 36 months | Permission Granted | 2025-03-24 09:30
2360793 | SG-015 | €6.1m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | Private | 28 | 25–49 | Mixed | 2025-03-21 | 2030-03-20 | More than 36 months | Permission Granted | 2025-10-21 07:28
2460304 | SG-015 | €6.2m - Residential Development, Adare | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | Private | 25 | 25–49 | Houses | 2025-03-21 | 2030-03-20 | More than 36 months | Permission Granted | 2024-06-27 09:16
2360703 | U-1310780 | €27m - Mixed Use Development, Dooradoyle | Limerick City and Suburbs | Limerick City West | Dooradoyle | Private | 104 | 100+ | Apartments | 2025-04-14 | 2030-04-13 | More than 36 months | Tender | 2026-07-24 10:14
2460633 | U-1353358 | €2.7m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City North | City Centre | Private | 15 | 10–24 | Apartments | 2025-04-24 | 2030-04-23 | More than 36 months | Permission Granted | 2025-03-26
21580 | U-1164424 | €9.6m - Residential Development | Limerick City and Suburbs | Limerick City East | Singland/Garryowen | Private | 55 | 50–99 | Mixed | 2025-05-13 | 2030-05-12 | More than 36 months | Contract Awarded | 2025-05-23 08:31
2560169 | U-1393371 | €4.8m - Mixed Use Development, Limerick | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | Private | 30 | 25–49 | Apartments | 2025-08-13 | 2030-08-12 | More than 36 months | Permission Granted | 2025-07-30
2560546 | SG-026 | €7m - Residential/Commercial Development, Limerick | Other County Limerick | Limerick City West | City Centre | Private | 37 | 25–49 | Apartments | 2025-09-04 | 2030-09-03 | More than 36 months | Permission Granted | 2026-04-09 07:34
2460864 | U-1363929 | €4.2m - Residential Development | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | Private | 15 | 10–24 | Houses | 2025-09-18 | 2030-09-17 | More than 36 months | Permission Granted | 2024-09-02
2461282 | P-1382991 | €32m - LRD, Mungret | Mungret | Limerick City West | Dooradoyle | Private | 139 | 100+ | Mixed | 2025-09-24 | 2030-09-23 | More than 36 months | Permission Granted | 2025-10-15 09:30
2560113 | P-1389800 | €87m - Student Accommodation, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 196 | 100+ | Student | 2025-10-29 | 2030-10-28 | More than 36 months | Commencement Expected | 2026-04-28 07:58
2460713 | P-1357447 | €4.2m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City North | Singland/Garryowen | Private | 25 | 25–49 | Apartments | 2025-10-31 | 2030-10-30 | More than 36 months | Permission Granted | 2025-11-07 08:23
2560540 | U-1408292 | €7m - Apartment Development, Limerick City | Limerick City and Suburbs | Limerick City West | City Centre | Private | 48 | 25–49 | Apartments | 2025-11-10 | 2030-11-09 | More than 36 months | Permission Granted | 2026-01-12
2560156 | SG-004 | €15.9m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | Private | 63 | 50–99 | Houses | 2025-11-11 | 2030-11-10 | More than 36 months | Permission Granted | 2025-11-21 13:41
2560653 | SG-004 | €9.4m - Residential Development | Patrickswell | Limerick City West | Outside city neighbourhoods | Private | 40 | 25–49 | Houses | 2026-01-20 | 2031-01-19 | More than 36 months | Stalled or Suspended | 2026-09-08 07:05 | On hold / no movement
2560780 | U-1412002 | €95m - Dock Road LRD, Limerick | Limerick City and Suburbs | Limerick City West | City Centre | Public – LDA | 285 | 100+ | Apartments | 2026-02-11 | 2031-02-10 | More than 36 months | Tender | 2026-09-07 10:12
2560595 | SG-032 | €819k - 6 Apartments | Other County Limerick | Limerick City West | City Centre | Private | 6 | 1–9 | Apartments | 2026-02-11 | 2031-02-10 | More than 36 months | Permission Granted | 2026-03-05 08:53
2560778 | U-1412257 | €1.2m - 10 Houses, Crossagalla | Kilmallock | Limerick City East | Southhill | Private | 10 | 10–24 | Houses | 2026-02-24 | 2031-02-23 | More than 36 months | Contract Awarded | 2026-07-14 06:26
2561211 | U-1417331 | €1.8m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | Private | 10 | 10–24 | Apartments | 2026-02-26 | 2031-02-25 | More than 36 months | Contract Awarded | 2026-09-09 07:34
2461182 | P-1379266 | €5.4m - Residential Development | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 27 | 25–49 | Mixed | 2026-03-30 | 2031-03-29 | More than 36 months | Permission Granted | 2026-04-17 07:40
2560633 | SG-004 | €2.4m - 6 Houses | Patrickswell | Limerick City West | Outside city neighbourhoods | Private | 6 | 1–9 | Houses | 2026-04-01 | 2031-03-31 | More than 36 months | Permission Granted | 2026-03-04 08:38
2560425 | SG-035 | €4.4m - Apartment Development | Limerick City and Suburbs | Limerick City West | Dooradoyle | Private | 24 | 10–24 | Apartments | 2026-04-14 | 2031-04-13 | More than 36 months | Permission Granted | 2026-04-23 14:03
2560271 | SG-002 | €21m - Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 114 | 100+ | Mixed | 2026-04-15 | 2031-04-14 | More than 36 months | Permission Granted | 2026-04-24 07:32
2560953 | P-1414128 | €4.8m - Residential Development, Limerick | Limerick City and Suburbs | Limerick City North | Corbally/Grove Island | Private | 25 | 25–49 | Mixed | 2026-04-29 | 2031-04-28 | More than 36 months | Permission Granted | 2026-04-02 11:17
2560771 | P-1411773 | €4.5m - Mixed Use Development | Limerick City and Suburbs | Limerick City West | City Centre | Private | 22 | 10–24 | Apartments | 2026-06-08 | 2031-06-07 | More than 36 months | Permission Granted | 2026-05-06 06:29
2561242 | SG-017 | €14.5m - Residential Development, Limerick | Other County Limerick | Limerick City West | City Centre | Private | 76 | 50–99 | Apartments | 2026-06-10 | 2031-06-09 | More than 36 months | Permission Granted | 2026-05-12 07:41
2560365 | P-1401743 | €2.4m - Apartment Development | Other County Limerick | Limerick City West | City Centre | Private | 16 | 10–24 | Apartments | 2026-06-16 | 2031-06-15 | More than 36 months | Permission Granted | 2025-04-29 06:04
2560399 | P-1402906 | €16.4m - Residential Development | Annacotty | Limerick City East | Castletroy/Annacotty | Private | 76 | 50–99 | Mixed | 2026-07-13 | 2031-07-12 | More than 36 months | Permission Granted | 2026-07-24 07:42
2660089 | P-1423228 | €42m - Large Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 465 | 100+ | Student | 2026-07-22 | 2031-07-21 | More than 36 months | Permission Granted | 2026-08-05 13:58
2660603 | P-1437215 | €84m - Parkway Valley LRD, Singland | Other County Limerick | Limerick City East | Southhill | Private | 403 | 100+ | Apartments | 2026-07-22 | 2031-07-22 | More than 36 months | Permission Granted | 2026-08-28 07:17
2561232 | P-1417746 | €9.4m - Student Accommodation Development, Limerick | Other County Limerick | Limerick City North | Singland/Garryowen | Private |  | Unknown | Student | 2026-07-28 | 2031-07-27 | More than 36 months | Permission Granted | 2026-04-07 06:56
2561231 | SG-020 | €32.5m - Large Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | Private | 169 | 100+ | Mixed | 2026-07-30 | 2031-07-30 | More than 36 months | Permission Granted | 2026-08-21 12:58
2561323 | SG-019 | €757k - 4 Apartments, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 4 | 1–9 | Apartments | 2026-07-30 | 2031-07-30 | More than 36 months | Permission Granted | 2026-08-28 08:24
2660241 | P-1446288 | €125.6m - Large Residential Development, Castletroy | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 523 | 100+ | Apartments | 2026-04-28 | 2031-09-01 | More than 36 months | Permission Granted | 2026-09-11 07:43
2660779 | P-1444384 | €8.6m - Staff Accommodation/8Apartments, Adare | Adare | Adare-Rathkeale | Outside city neighbourhoods | Private | 28 | 25–49 | Apartments | 2026-09-02 | 2031-09-02 | More than 36 months | Permission Granted | 2026-09-07 08:36
2560947 | P-1414007 | €1m - 8 Houses, Bruff | Bruff | Cappamore-Kilmallock | Outside city neighbourhoods | Private | 8 | 1–9 | Houses | 2026-09-02 | 2031-09-02 | More than 36 months | Permission Granted | 2026-09-07 07:52
2660396 | P-1432711 | €39m - Large Residential Development, Mungret | Mungret | Limerick City West | Dooradoyle | Private | 182 | 100+ | Mixed | 2026-09-15 | 2031-09-15 | More than 36 months | Permission Granted | 2026-09-21 08:22
2660275 | P-1428325 | €42m - Large Residential Development,Limerick | Limerick City and Suburbs | Limerick City East | Castletroy/Annacotty | Private | 212 | 100+ | Mixed | 2026-09-23 | 2031-09-22 | More than 36 months | Permission Granted | 2026-08-24 08:10
228020 | P-1258895 | €4.9m - Residential Development, Newcastle West | Newcastle West | Newcastle West | Outside city neighbourhoods | Public – local authority | 31 | 25–49 | Unknown | 2023-02-10 |  | No expiry date (mainly Part 8) | Permission Granted | 2023-02-22 11:24
198010 | SG-015 | €5m - Housing Development | Rathkeale | Adare-Rathkeale | Outside city neighbourhoods | Public – local authority | 31 | 25–49 | Apartments | 2020-01-27 |  | No expiry date (mainly Part 8) | Permission Granted | 2019-11-12 14:24
198004 | P-1054214 | €6m - Residential Development, King's Island | Other County Limerick | Limerick City North | Kings Island | Public – local authority | 27 | 25–49 | Apartments | 2019-10-02 |  | No expiry date (mainly Part 8) | Permission Granted | 2023-03-13 10:58
Part 8 - 1248404 | SG-004 | €4.6m - Residential Development, Patrickswell | Patrickswell | Limerick City West | Outside city neighbourhoods | Public – local authority | 24 | 10–24 | Unknown | 2023-01-24 |  | No expiry date (mainly Part 8) | Permission Granted | 2023-03-02 11:12
| U-1422145 | €719k - Architect Led Integrated Design Team Services for 23 Residential Units, Limerick | Limerick City and Suburbs | Limerick City North | Kings Island | Public – local authority | 23 | 10–24 | Unknown |  |  | No expiry date (mainly Part 8) | Contract Awarded | 2026-06-30 09:18
Part 8 - 1371977 | SG-035 | €3.4m - Residential Development | Limerick City and Suburbs | Limerick City West | Dooradoyle | Public – local authority | 20 | 10–24 | Apartments | 2025-01-20 |  | No expiry date (mainly Part 8) | Permission Granted | 2025-02-05 13:57
198009 | P-1071780 | €1.8m - Housing Development | Other County Limerick | Limerick City East | Outside city neighbourhoods | Public – local authority | 12 | 10–24 | Houses | 2019-12-12 |  | No expiry date (mainly Part 8) | Permission Granted | 2019-11-11 13:52
258297 | U-1414882 | €4.5m - Residential Development, Abbeyfeale | Abbeyfeale | Newcastle West | Outside city neighbourhoods | Public – approved housing body | 12 | 10–24 | Houses |  |  | No expiry date (mainly Part 8) | Tender | 2026-06-08 08:26
Part 8 - 1264155 | SG-031 | €590k - Residential Development / Living Georgian Project, 58 O’Connell Street | Other County Limerick | Limerick City West | City Centre | Public – local authority | 8 | 1–9 | Unknown | 2022-04-08 |  | No expiry date (mainly Part 8) | Permission Granted | 2022-12-22 12:05
188013 | P-1007351 | €701k - 7 Houses | Abbeyfeale | Newcastle West | Outside city neighbourhoods | Public – local authority | 7 | 1–9 | Houses | 2018-09-25 |  | No expiry date (mainly Part 8) | Permission Granted | 2018-09-03 14:54
PT8LL277 | U-1412368 | €1.5m - 5 Residential Units, Limerick | Limerick City and Suburbs | Limerick City East | Southhill | Public – local authority | 5 | 1–9 | Unknown | 2025-12-15 |  | No expiry date (mainly Part 8) | Tender | 2026-05-06 10:16
188004 |  | Part 8: (i) provision of 5 no. residential units (3 no. 2 bedroom houses and 2 | Limerick City and Suburbs | Limerick City North | Caherdavin | Public – local authority | 5 | 1–9 | Houses | 2018-06-13 |  | No expiry date (mainly Part 8) | Permission Granted
Part 8 - 1316160 | U-1316160 | €705k - Radharc an Ghleanna Residential Development, Mountcollins | Other County Limerick | Newcastle West | Outside city neighbourhoods | Public – local authority | 4 | 1–9 | Unknown | 2024-02-13 |  | No expiry date (mainly Part 8) | Tender | 2025-09-12 08:35
15577 | U-837963 | €588k - 3 Houses | Other County Limerick | Cappamore-Kilmallock | Outside city neighbourhoods | Public – local authority | 3 | 1–9 | Houses | 2015-09-09 |  | No expiry date (mainly Part 8) | Tender | 2017-03-13 10:06
| U-1417205 | €1.4m - Architect Led Integrated Design Team for College Avenue Infill Housing Scheme, Moyross | Limerick City and Suburbs | Limerick City North | Caherdavin | Public – local authority | 0 | Unknown | Unknown |  |  | No expiry date (mainly Part 8) | Contract Awarded | 2026-07-10 09:53
| U-1424651 | €20m - Council Housing Programme 2026 - 2030, Limerick | Limerick City and Suburbs | Unknown | Unknown | Public – local authority | 0 | Unknown | Unknown |  |  | No expiry date (mainly Part 8) | Tender | 2026-02-26 08:59
| U-1438055 | €1.5m - Multi-Party Framework for Maintenance Repairs and Replacement of Heating Systems, Limerick | Limerick City and Suburbs | Unknown | Unknown | Public – local authority |  | Unknown | Unknown |  |  | No expiry date (mainly Part 8) | Tender | 2026-06-17 07:59
Values calculated in delivery_analysis.py from the Schemes sheet.

## 8 Annual flows
Year | Units granted | Units started | Units completed (CIS)
2018 | 655 | 63 | 0
2019 | 481 | 161 | 0
2020 | 622 | 301 | 20
2021 | 1132 | 247 | 134
2022 | 1616 | 965 | 79
2023 | 880 | 713 | 185
2024 | 1402 | 1607 | 350
2025 | 1113 | 513 | 237
2026 | 2795 | 745 | 270
Values calculated in delivery_analysis.py from the Schemes sheet.

## 9 Build rates
Group | Completed schemes | Median build period (yrs) | Median build rate (dpa) | LQ dpa | UQ dpa
All completed | 47 | 1.8 | 8 | 4.2 | 17.8
1–9 | 18 | 1.7 | 4.1 | 2.3 | 5.8
10–24 | 15 | 1.8 | 8.3 | 6 | 11.2
25–49 | 6 | 1.4 | 21.5 | 17.7 | 26.6
50–99 | 4 | 2.3 | 34 | 24 | 44.2
100+ | 3 | 2.1 | 50.3 | 38.4 | 73.7
Houses | 22 | 1.7 | 4.2 | 2.6 | 12.1
Apartments | 9 | 1.8 | 8 | 5.3 | 10.7
Mixed | 8 | 2 | 34.3 | 20.9 | 50.3
Values calculated in delivery_analysis.py from the Schemes sheet.

## 10 Barrier indicators
Indicator | Schemes / applications | Units
Permitted schemes not started, permission live | 94 | 5143
Permitted schemes not started, past expiry | 14 | 311
Schemes recorded by CIS as stalled or suspended | 4 | 156
Schemes with CIS note: on hold / no movement | 9 | 666
Schemes with CIS note: legal challenge / quashed | 0 | 0
Schemes with CIS note: site for sale / sold | 2 | 98
Schemes where further information was requested | 163 | 6478
Schemes that went to appeal | 48 | 2703
Applications refused or withdrawn (not counted) | 14 | 518
Applications superseded by a later application | 3 | 90
Extensions of duration sought | 14
Values calculated in delivery_analysis.py from the Schemes sheet.

## 11 Data sources
Item | Value
Schemes in study (counted applications) | 265
Schemes with permission | 251
Start date from building control commencement notice | 132
Start date from CIS only | 10
Completed schemes (CIS and Department social housing report) | 47
Completed schemes with a completion certificate | 44
Units on completed schemes | 1275
Units on completion certificates for those schemes | 340
Part 8 schemes in study | 55
Part 8 schemes added from the register (not in CIS) | 10
Units on Part 8 schemes added from the register | 104
Public schemes (local authority, AHB, LDA) | 76
Units on public schemes | 1737
Values calculated in delivery_analysis.py from the Schemes sheet.